## Decision
FIGURE 3 PUBLICATION-CONSISTENCY CONTROL DECISION
As-of boundary | 2026-08-26T17:00:00+08:00 (Asia/Singapore) | Status | FINAL REVIEW RESULT
Case / gate | CASE-EMC-2026-0147 / GATE-0147 | Pre-audit gate | QA_REVIEW_OPEN
Linked components | Current proof PRF-02 and staged deposit DEP-V3 | Production lock | 2026-08-28T18:00:00+08:00
OVERALL DECISION | HOLD_CURRENT_PROOF_AND_LINKED_DEPOSIT | Proof state | HOLD — DO NOT RELEASE PRF-02
Business meaning | PRF-02 and DEP-V3 cannot be released as of the cutoff. A and B require correction, C requires restoration to the accepted annotation, D is clear, and final PQL re-review remains required. | Deposit state | HOLD_STAGED — DO NOT PUBLISH DEP-V3
Release condition | A legend corrected; B regenerated from R17 and linked wording corrected; C restored to n=42; mapped no-change checks completed; DEP-V3 README corrected and rows verified; corrected proof reapproved; PQL releases the shared gate. | Gate principle | HOLD has precedence while any mandatory correction, mapped synchronization, or final reapproval is open.
Decision basis | Publication-consistency only: component authority, visible proof-to-R17 agreement, mapped downstream synchronization, and coupled release control. No scientific-merit, causal-validity, misconduct, or substantive educational-effect conclusion is made. | Centre-rule sources | Workspace/01_Governance/publication_release_policy.pdf ¦ page[3] display tolerance; page[5] coupled HOLD precedence
Trigger | Production alert: cohort labels and uncertainty whiskers appeared inconsistent; this initiated a consistency review, not a scientific-validity inquiry. | Source | Workspace/01_Governance/accepted_submission_manifest.xlsx ¦ Proof_Events!A2:H2
PANEL CONTROL SUMMARY
Panel | Controlling authority and observed conclusion | Disposition | Immediate owner / due
FIG3-A | FIG3-LR2 authorized for A. Proof pixels pair teal with Non-incentivized and amber with Incentivized; R17 requires the reverse pairing. Both estimates and intervals pass. | CORRECT_PROOF_LEGEND | PD-EDITOR / 2026-08-27T10:00:00+08:00
FIG3-B | FIG3-LR2 authorized for B. Visible 0.02 [-0.01, 0.11] versus R17 0.02 [-0.01, 0.07]; upper variance +0.04 fails both limits. | CORRECT_PROOF_AND_LINKED_TEXT | EMC-STAT 09:30 confirmation; PD-EDITOR 12:00 regeneration
FIG3-C | FIG3-ACC-v5 remains controlling because C was never requested or approved. Proof pixels show n=24; accepted baseline and R17 require n=42. Estimate and interval pass. | REVERT_TO_ACCEPTED_ANNOTATION | PD-EDITOR / 2026-08-27T10:00:00+08:00
FIG3-D | FIG3-ACC-v5 controls D. Visible median 0.02, interval [-0.04, 0.08], unit, labels, order, and no-marker state all pass. | CLEAR — RETAIN UNCHANGED | PD-EDITOR records verification / 2026-08-27T10:00:00+08:00

## Panel_Reconciliation
PANEL-LEVEL RECONCILIATION — VISUAL + STRUCTURED + AUTHORITY
Panel ID | Visibly displayed in PRF-02 | Controlling expected value / label | Variance and tolerance result | Controlling version | Approval / authority state | Comparison result | Disposition | Downstream impact | Required panel action | Primary owner | Due time (Asia/Singapore) | Visual evidence locator | Structured / approval evidence locator | Observable business conclusion
FIG3-A | Teal mark 0.04 [-0.02, 0.10] with legend teal→Non-incentivized; amber mark -0.01 [-0.07, 0.05] with legend amber→Incentivized. | R17: teal→Incentivized, 0.04 [-0.02, 0.10]; amber→Non-incentivized, -0.01 [-0.07, 0.05]. | All six numeric marks: variance 0.00, PASS (≤0.005 and within one pixel). Both exact swatch-to-cohort labels: FAIL; colour/category equality is mandatory. | FIG3-LR2 | AUTHORIZED FOR A: RR-017 requested A; CA and PQL approved the same LR2 hash. Proof-to-R17 verification remained mandatory. | Numeric geometry PASS; legend mapping FAIL. | CORRECT_PROOF_LEGEND — retain authorized LR2 after correction. | CAP-3A and RS-3A verify/no text change; DEP-README-COLOR must be corrected. | Swap only the proof legend labels so teal=Incentivized and amber=Non-incentivized; preserve R17 marks. | PD-EDITOR | 2026-08-27T10:00:00+08:00 | Workspace/04_Proof/current_production_proof_PRF-02.pdf ¦ page[6].image[0], FIG3-A; Workspace/04_Proof/figure3_current_proof_extracted.png ¦ native bounds [80,90,1190,870]. Direct pixel inspection shows the two displayed swatch/label pairings. | Workspace/03_Analysis/fig3_analysis_export_R17.xlsx ¦ Panel_Estimates!A2:M3; Display_Map!A2:H3. Workspace/01_Governance/late_replacement_approval_log.pdf ¦ pages[1]-[3]. Workspace/01_Governance/publication_release_policy.pdf ¦ page[3]. | A is an authorized production component with one mandatory encoding defect; it cannot clear until the legend is corrected.
FIG3-B | Calibrated whisker visibly reads median 0.02, lower -0.01, upper 0.11. | R17: median 0.02, 95% interval [-0.01, 0.07] standardized delta-z. | Median 0.00 PASS; lower 0.00 PASS; upper +0.04 FAIL. +0.04 exceeds inclusive 0.005 and the one-rendered-pixel limit. | FIG3-LR2 | AUTHORIZED FOR B: RR-017 requested B; CA and PQL approved the same LR2 hash. Proof-to-R17 verification remained mandatory. | Median/lower PASS; upper endpoint FAIL. | CORRECT_PROOF_AND_LINKED_TEXT — regenerate from R17. | CAP-3B and RS-3B change upper endpoint to 0.07; SUP-F3 label changes to R17; DEP-3B verify/no change. | EMC-STAT confirms FIG3-B export, then PD-EDITOR regenerates the proof whisker from R17; synchronize linked text. | EMC-STAT; PD-EDITOR | 2026-08-27T09:30:00+08:00; 2026-08-27T12:00:00+08:00 | Workspace/04_Proof/current_production_proof_PRF-02.pdf ¦ page[6].image[0], FIG3-B; Workspace/04_Proof/figure3_current_proof_extracted.png ¦ native bounds [1210,90,2320,870], calibrated axis -0.10..0.20. Approx. native x: axis 1430..2201; whisker 1661..1970; median 1738, resolving to -0.01..0.11 and 0.02. | Workspace/03_Analysis/fig3_analysis_export_R17.xlsx ¦ Panel_Estimates!A4:M4; Display_Map!A4:H4. Workspace/04_Proof/proof_component_inventory.json ¦ /figure_components/FIG3/render_calibration and /panel_bounds/FIG3-B. Workspace/01_Governance/publication_release_policy.pdf ¦ page[3]. Workspace/01_Governance/late_replacement_approval_log.pdf ¦ pages[1]-[3]. | B is authorized but its current uncertainty display and textual echoes are out of tolerance; proof regeneration is required.
FIG3-C | Proof panel visibly prints n=24; its mark reads 0.06 [0.01, 0.14]. | Accepted FIG3-ACC-v5 and R17 require n=42; expected mark 0.06 [0.01, 0.14]. | Median/endpoints variance 0.00 PASS. Exact annotation: 24≠42, FAIL (no tolerance). Authority test FAIL for changed annotation. | FIG3-ACC-v5 | C was not requested and not approved by CA or PQL; composite LR2 does not supersede accepted C. | Estimate/interval PASS; annotation and replacement authority FAIL. | REVERT_TO_ACCEPTED_ANNOTATION. | CAP-3C and DEP-3C verify/no change. | Restore visible n=42 from accepted baseline; do not treat C as an approved replacement. | PD-EDITOR | 2026-08-27T10:00:00+08:00 | Workspace/04_Proof/current_production_proof_PRF-02.pdf ¦ page[6].image[0], FIG3-C; Workspace/04_Proof/figure3_current_proof_extracted.png ¦ native bounds [80,930,1190,1710], visibly n=24. Workspace/02_Manuscript/accepted_manuscript_AM-2026-0147-v5.pdf ¦ page[11].image[0], FIG3-C, visibly n=42. | Workspace/03_Analysis/fig3_analysis_export_R17.xlsx ¦ Panel_Estimates!A5:M5; Display_Map!A5:H5. Workspace/01_Governance/late_replacement_approval_log.pdf ¦ pages[2]-[3], C=not requested/not approved. Workspace/01_Governance/accepted_submission_manifest.xlsx ¦ Accepted_Set!A3:H3. | C must be restored to the accepted annotation because the visible change is both inconsistent and outside approved scope.
FIG3-D | Visible median 0.02; interval [-0.04, 0.08]; “Standardized Δz”; “95% interval”; labels Incentivized then Non-incentivized; no exploratory marker. | R17/accepted D: 0.02 [-0.04, 0.08], standardized delta-z, same labels/order, no exploratory marker. | Median/endpoints variance 0.00 and within one pixel; unit, interval label, category order, required labels, marker absence, identity, and authority all PASS exact checks. | FIG3-ACC-v5 | D was not requested or approved for replacement; accepted baseline controls and current pixels match it. | ALL mandatory dimensions PASS. | CLEAR — retain unchanged. | CAP-3D, RS-3D, and DEP-3D verify/no change. | Retain D unchanged; record mapped no-change checks. | PD-EDITOR | 2026-08-27T10:00:00+08:00 | Workspace/04_Proof/current_production_proof_PRF-02.pdf ¦ page[6].image[0], FIG3-D; Workspace/04_Proof/figure3_current_proof_extracted.png ¦ native bounds [1210,930,2320,1710]. Direct inspection supports mark geometry, unit, interval label, label order, and no-marker state. | Workspace/03_Analysis/fig3_analysis_export_R17.xlsx ¦ Panel_Estimates!A6:M6; Display_Map!A6:H9. Workspace/01_Governance/late_replacement_approval_log.pdf ¦ pages[2]-[3], D=not requested/not approved. Workspace/02_Manuscript/accepted_manuscript_AM-2026-0147-v5.pdf ¦ page[11].image[0], FIG3-D. | D is the unaffected control and clears independently; its clearance does not release A-C or the coupled gate.

## Dimension_Checks
MANDATORY DIMENSION CHECKS — ONE FAILURE PREVENTS CLEARANCE
Check ID | Panel | Mandatory dimension | Observed from controlling/current pixels | Expected from controlling structured/accepted source | Variance / exact comparison | Tolerance rule | Result | Visual locator | Structured / authority locator
A-NUM-TEAL | FIG3-A | teal estimate + both endpoints | 0.04 [-0.02, 0.10] | 0.04 [-0.02, 0.10] | 0.00 for all marks | ≤0.005 and ≤1 pixel | PASS | PRF-02 page[6].image[0], FIG3-A; extracted PNG bounds [80,90,1190,870] | R17 Panel_Estimates!A2:M2
A-NUM-AMBER | FIG3-A | amber estimate + both endpoints | -0.01 [-0.07, 0.05] | -0.01 [-0.07, 0.05] | 0.00 for all marks | ≤0.005 and ≤1 pixel | PASS | PRF-02 page[6].image[0], FIG3-A; extracted PNG bounds [80,90,1190,870] | R17 Panel_Estimates!A3:M3
A-MAP-TEAL | FIG3-A | teal cohort label | Non-incentivized | Incentivized | not equal | exact label/colour equality | FAIL | PRF-02 page[6].image[0], FIG3-A legend | R17 Display_Map!A2:H2
A-MAP-AMBER | FIG3-A | amber cohort label | Incentivized | Non-incentivized | not equal | exact label/colour equality | FAIL | PRF-02 page[6].image[0], FIG3-A legend | R17 Display_Map!A3:H3
A-AUTH | FIG3-A | authorization | LR2 hash proof-linked; A requested and approved | FIG3-LR2 | all authority predicates present | exact component scope | PASS | PRF-02 page[6].image[0] | Approval log pages[1]-[3]; inventory /attachment_history/FIG3-LR2
B-MED | FIG3-B | median | 0.02 | 0.02 | 0.00 | ≤0.005 and ≤1 pixel | PASS | PRF-02 page[6].image[0], B; extracted bounds [1210,90,2320,870] | R17 Panel_Estimates!D4
B-LOW | FIG3-B | lower 95% endpoint | -0.01 | -0.01 | 0.00 | ≤0.005 and ≤1 pixel | PASS | same B calibrated pixel locator | R17 Panel_Estimates!E4
B-UP | FIG3-B | upper 95% endpoint | 0.11 | 0.07 | +0.04 | ≤0.005 and ≤1 pixel | FAIL | same B calibrated pixel locator; native whisker right x≈1970 | R17 Panel_Estimates!F4; policy page[3]
B-LABELS | FIG3-B | identity, unit, axis, 95% label | Immediate minus Delayed; Standardized Δz; -0.10..0.20; 95% interval | same | exact agreement | exact | PASS | PRF-02 page[6].image[0], B | R17 Panel_Estimates!B4:C4,G4:J4; Display_Map!A4:H4
B-AUTH | FIG3-B | authorization | LR2 hash proof-linked; B requested and approved | FIG3-LR2 | all authority predicates present | exact component scope | PASS | PRF-02 page[6].image[0] | Approval log pages[1]-[3]; inventory /attachment_history/FIG3-LR2
C-MARKS | FIG3-C | median + both endpoints | 0.06 [0.01, 0.14] | 0.06 [0.01, 0.14] | 0.00 for all marks | ≤0.005 and ≤1 pixel | PASS | PRF-02 page[6].image[0], C; extracted bounds [80,930,1190,1710] | R17 Panel_Estimates!D5:F5
C-ANNOT | FIG3-C | sample annotation | n=24 | n=42 | 24≠42 | exact annotation | FAIL | PRF-02 page[6].image[0], C visibly n=24; accepted page[11].image[0], C visibly n=42 | R17 Panel_Estimates!L5; Display_Map!A5:H5
C-AUTH | FIG3-C | authorization | C not requested / not approved | FIG3-ACC-v5 controls | replacement authority absent | exact component scope | FAIL for changed component | PRF-02 page[6].image[0], C | Approval log pages[2]-[3]; manifest Accepted_Set!A3:H3
D-ID | FIG3-D | panel identity/title | Pre-registered moderator | Pre-registered moderator | equal | exact | PASS | PRF-02 page[6].image[0], D | R17 Panel_Estimates!B6:C6
D-MED | FIG3-D | median | 0.02 | 0.02 | 0.00 | ≤0.005 and ≤1 pixel | PASS | PRF-02 page[6].image[0], D; extracted bounds [1210,930,2320,1710] | R17 Panel_Estimates!D6
D-LOW | FIG3-D | lower 95% endpoint | -0.04 | -0.04 | 0.00 | ≤0.005 and ≤1 pixel | PASS | same D pixel locator | R17 Panel_Estimates!E6
D-UP | FIG3-D | upper 95% endpoint | 0.08 | 0.08 | 0.00 | ≤0.005 and ≤1 pixel | PASS | same D pixel locator | R17 Panel_Estimates!F6
D-UNIT | FIG3-D | unit | Standardized Δz | standardized delta-z / Standardized Δz | semantic and visible exact display match | exact unit | PASS | same D pixel locator | R17 Panel_Estimates!G6; Display_Map!A8:H8
D-ORDER | FIG3-D | category order | Incentivized then Non-incentivized | Incentivized then Non-incentivized | equal | exact | PASS | same D pixel locator | R17 Display_Map!A6:H6
D-LABEL | FIG3-D | interval and category labels | 95% interval; Incentivized; Non-incentivized | same | equal | exact | PASS | same D pixel locator | R17 Display_Map!A6:H9; accepted page[11].image[0], D
D-MARKER | FIG3-D | exploratory marker | absent | false / absent | equal | exact absence mandatory | PASS | same D pixel locator | R17 Display_Map!A7:H7
D-AUTH | FIG3-D | authorization | D not requested/approved; accepted component visibly retained | FIG3-ACC-v5 controls | accepted authority preserved | exact component scope | PASS | PRF-02 page[6].image[0], D; accepted page[11].image[0], D | Approval log pages[2]-[3]; manifest Accepted_Set!A3:H3

## Evidence_Lineage
BYTE-VERIFIED CONTROLLING LINEAGE
Step | Source object / role | Public source and exact locator | Run / object ID | Effective / completion time | Declared digest / identity | Recomputed observation | Relationship / ordering test | Result
1 | OBS-R17 approved input rows | Workspace/03_Analysis/analysis_observations_R17.csv ¦ header row 1; records rows 2:5281; qc_flag column H | OBS-R17 / AR-2026-08-24-R17 | Consumed by export completed 2026-08-24T22:14:00+08:00 | 7381f1740a23ca4af11b780e78c003869d0590a990e5b984caa7c613555c018c | Full-file SHA-256 recomputed equal; 5,280 data rows; 5,112 include; 168 exclude_predeclared; 5,280 unique participant keys; every row names R17. | OBS bytes are the sole input hash recorded in export and environment. | PASS
2 | Finalized structured export | Workspace/03_Analysis/fig3_analysis_export_R17.xlsx ¦ Run_Manifest!A2:B11; QC_Summary!A2:D5 | FIG3-EST-R17 / AR-2026-08-24-R17 | run completed 2026-08-24T22:14:00+08:00; approved 2026-08-25T16:00:00+08:00; serialization completed 2026-08-26T07:55:00+08:00 | cd122e8b72c520eba3c8efa9f96799f3de579f9353cdb6712b337fe6f0c01113 | Full-file SHA-256 recomputed equal; approval_flag=publication_export; input hash equals step 1; QC totals recompute. | OBS-R17 → finalized FIG3-EST-R17. Finalization precedes environment attestation. | PASS
3 | Environment attestation | Workspace/03_Analysis/analysis_environment_R17.json ¦ /analysis_run_id, /input_observations_sha256, /output_workbook_sha256, /approval_flag, /attested_at, /packages | AR-2026-08-24-R17 / FIG3-EST-R17 | attested 2026-08-26T08:05:00+08:00 | input 7381f...c018c; output cd122e...01113 | Both full digests equal recomputed steps 1 and 2; R 4.5.1, brms 2.22.0, posterior 1.6.1, ggplot2 3.5.2; code 8f2c7e1. | Attestation 08:05 is 10 minutes after export serialization 07:55 (non-earlier). | PASS
4 | Accepted authority link | Workspace/01_Governance/accepted_submission_manifest.xlsx ¦ Accepted_Set!A4:H5; Version_History!A5:G6 | AR-2026-08-24-R17 / FIG3-EST-R17 | approved/effective 2026-08-25T16:00:00+08:00 | export cd122e8b72c520eba3c8efa9f96799f3de579f9353cdb6712b337fe6f0c01113 | Manifest export digest equals recomputed step 2; R16 rows explicitly superseded; rollback_event_id null. | Approved manifest selects R17, not R16. | PASS
5 | LR2 request and approvals | Workspace/01_Governance/late_replacement_approval_log.pdf ¦ page[1] request/hash; page[2] CA approval/hash; page[3] PQL approval/hash/proof link | FIG3-LR2 / RR-017 / APPR-RR017-CA / APPR-RR017-PQL | 08:55 request; 10:40 CA approval; 12:20 PQL approval on 2026-08-26 | 779d11a0b97371edf7296b7818d83c8c5e93ac78da2a67f3b9b31c44e47106b5 | Printed hash equals recomputed standalone extracted PNG digest and proof inventory digest; scope A/B only. | Exact attachment identity plus scoped authority; hash does not expand scope. | PASS
6 | Proof / attachment identity | Workspace/04_Proof/proof_component_inventory.json ¦ /proof; /figure_components/FIG3; /attachment_history/FIG3-LR2. Workspace/04_Proof/current_production_proof_PRF-02.pdf ¦ page[6].image[0]. Workspace/04_Proof/figure3_current_proof_extracted.png ¦ full file | PRF-02 / FIG3-LR2 | proof built 2026-08-26T09:18:00+08:00 | proof 6ed5d5954db9225c97e69adba54f9196c7a162c2df060f5c0c3ae4b71c19b347; image 779d11a...47106b5 | Proof PDF full-file and extracted PNG digests recomputed equal to inventory. PDF image extraction and standalone PNG compare at 0 differing pixels; dimensions 2400×1800. | PRF-02 page[6].image[0] is the approved LR2 rendition. | PASS
7 | Staged repository projection | Workspace/06_Deposit/deposit_v3_manifest.xlsx ¦ File_Inventory!A2:I2; Panel_Data!A2:H5 | DEP-V3 / FIG3-EST-R17 / AR-2026-08-24-R17 | staged 2026-08-26T08:40:00+08:00 | cd122e8b72c520eba3c8efa9f96799f3de579f9353cdb6712b337fe6f0c01113 | Inventory digest equals recomputed export; Panel_Data values for A-D match R17 rows; state=staged. | DEP-V3 is the R17 projection, not a substitute authority and not yet releasable. | PASS
8 | Lineage conclusion | Steps 1–7 above; Workspace/06_Deposit/deposit_version_history.csv ¦ rows 2:3 | R17 controlling set | as of 2026-08-26T17:00:00+08:00 | OBS 7381f...c018c → export cd122e...01113; LR2 image 779d...106b5 | No conflicting digest; all times parse before cutoff; no alternative input, later workbook mutation, rollback, or invalidation found. | CONTROLLING STRUCTURED EVIDENCE = 5,112 included OBS-R17 rows → finalized FIG3-EST-R17 under AR-2026-08-24-R17 → later environment attestation; DEP-V3 is its staged projection. | PASS

## Authority_History
CUTOFF, COMPONENT AUTHORITY, AND BOUNDED HISTORICAL TREATMENT
Record / state | Time eligibility at cutoff | Authority links | Current successor / controlling relation | Rollback or invalidation test | Treatment at cutoff | Precise public locator
Evidence cutoff | 2026-08-26T17:00:00+08:00, Asia/Singapore | Eligibility does not create authority | Filters all following records | n/a | Apply cutoff first. | Workspace/01_Governance/publication_release_policy.pdf ¦ pages[1]-[2]; Workspace/07_Release_Control/production_lock_schedule.md ¦ lines 3:5
CHK-0147-R16 | Eligible historical event: 2026-08-19T14:30:00+08:00 | Links FIG3-ACC-v5 + AR-2026-08-18-R16; all panels CLEAR only for that state | Current A/B LR2 and analysis R17 links exist | rollback_event_id=null | HISTORICAL / SUPERSEDED CONTEXT. Never use its CLEAR cells to clear current A/B. | Workspace/01_Governance/accepted_submission_manifest.xlsx ¦ Checklist_History!A2:J2; Version_History!A5:G6
DEP-V2 | Eligible predecessor: 2026-08-19T16:00:00+08:00 | AR-2026-08-18-R16; public access | successor_version_id=DEP-V3; V3 is staged R17 projection | rollback_event_id=null for V2/V3 | HISTORICAL PUBLIC PREDECESSOR. Preserve public availability; make current decision against DEP-V3. | Workspace/06_Deposit/deposit_version_history.csv ¦ rows 2:3
SUP-F3 printed R16 label | Eligible accepted-manuscript record | Printed AR-2026-08-18-R16 label; dependency-map link hash is current R17 export cd122e...01113 | R17 export is approved and byte-linked | No R17 invalidation or link restoration to R16 | STALE LABEL ONLY. Correct printed label to R17; retain existing R17 link and history. | Workspace/02_Manuscript/accepted_manuscript_AM-2026-0147-v5.pdf ¦ page[10]; Workspace/05_Dependencies/panel_content_dependency_map.xlsx ¦ Dependencies!A7:I7
FIG3-LR3 / Figure3_final_v9.png | Time-eligible arrival: 2026-08-26T16:40:00+08:00 | request_id=null; author approval=null; PQL approval=null; proof link=null; different digest 536e...89566 | LR2 remains approved and inserted at PRF-02 page[6].image[0] | No missing authority field became valid by cutoff | ELIGIBLE BUT NONCONTROLLING ORPHAN HISTORY. Filename recency does not select authority. | Workspace/01_Governance/late_replacement_approval_log.pdf ¦ page[4]; Workspace/04_Proof/proof_component_inventory.json ¦ /attachment_history/FIG3-LR3
Current panel authority | All request/approval/proof-link events ≤ cutoff | LR2 exact hash + RR-017 + CA + PQL name A/B only | A/B=FIG3-LR2; C/D=FIG3-ACC-v5 | No eligible rollback or invalidation in manifest, deposit history, or approval log | CONTROLLING: scoped current links. | Workspace/01_Governance/late_replacement_approval_log.pdf ¦ pages[1]-[3]; Workspace/01_Governance/accepted_submission_manifest.xlsx ¦ Accepted_Set!A3:H5, Version_History!A4:G6
Current analysis/deposit authority | R17 approved 2026-08-25; DEP-V3 staged 2026-08-26 08:40 | R17 publication_export + exact OBS/export hashes; V3 inventory matches | R17 controls structured evidence; DEP-V3 is staged projection | rollback_event_id=null; no invalidation | CONTROLLING R17/LR2/V3 chain; V3 remains HOLD_STAGED. | Workspace/03_Analysis/fig3_analysis_export_R17.xlsx ¦ Run_Manifest!A2:B11; Workspace/06_Deposit/deposit_v3_manifest.xlsx ¦ File_Inventory!A2:I2; deposit_version_history.csv ¦ row 3

## Downstream_Impact
DEPENDENCY CONSERVATION — 11 PHYSICAL MAP ROWS / 12 STABLE ENDPOINT IDS
Map row | Panel | Endpoint ID(s) | Endpoint type | Mapped current locator | Current content observation | Outcome | Exact edit or no-change action | Primary owner | Due time | Dependency-map evidence | Current-content evidence
2 | FIG3-A | CAP-3A | caption clause | AM page 11; PRF page 6 | Already says teal=Incentivized and amber=Non-incentivized. | VERIFY / NO TEXT CHANGE | Verify after proof legend correction; retain text. | CA-STUDY | 2026-08-27T10:30:00+08:00 | Dependencies!A2:I2 | Accepted manuscript page[11]; PRF-02 page[6]
3 | FIG3-A | RS-3A | results statement | AM page 8; PRF page 7 | Refers to caption mapping; does not state reversed mapping. | VERIFY / NO TEXT CHANGE | Verify against corrected legend; retain text. | CA-STUDY | 2026-08-27T10:30:00+08:00 | Dependencies!A3:I3 | Accepted manuscript page[8]; PRF-02 page[7]
4 | FIG3-A | DEP-README-COLOR | deposit README entry | README_Entries row 2 | Currently says teal=Non-incentivized and amber=Incentivized. | EDIT | Correct exactly to teal=Incentivized and amber=Non-incentivized. | REPO-STEW | 2026-08-27T12:00:00+08:00 | Dependencies!A4:I4 | deposit_v3_manifest.xlsx ¦ README_Entries!A2:E2
5 | FIG3-B | CAP-3B | caption clause | PRF page 6 | Currently upper 95% endpoint=0.11. | EDIT | Change upper endpoint to 0.07. | CA-STUDY | 2026-08-27T10:30:00+08:00 | Dependencies!A5:I5 | PRF-02 page[6]
6 | FIG3-B | RS-3B | results statement | PRF page 7 | Currently says interval extends to 0.11. | EDIT | Change upper endpoint to 0.07. | CA-STUDY | 2026-08-27T10:30:00+08:00 | Dependencies!A6:I6 | PRF-02 page[7]
7 | FIG3-B | SUP-F3 | supplement reference | AM page 10 | Printed run label R16; link hash already equals current R17 export. | EDIT LABEL / RETAIN LINK | Change printed run label to AR-2026-08-24-R17; retain cd122e...01113 R17 link. | CA-STUDY | 2026-08-27T10:30:00+08:00 | Dependencies!A7:I7 | Accepted manuscript page[10]; Dependencies!H7
8 | FIG3-B | DEP-3B | deposit panel row | Panel_Data row 3 | 0.02 [-0.01,0.07], R17 — matches controlling export. | VERIFY / NO CHANGE | Verify row and identity; retain values. | REPO-STEW | 2026-08-27T12:00:00+08:00 | Dependencies!A8:I8 | deposit_v3_manifest.xlsx ¦ Panel_Data!A3:H3; R17 Panel_Estimates!A4:M4
9 | FIG3-C | CAP-3C | caption clause | AM page 11; PRF page 6 | Already says n=42. | VERIFY / NO TEXT CHANGE | Verify after proof annotation restoration; retain text. | CA-STUDY | 2026-08-27T10:30:00+08:00 | Dependencies!A9:I9 | Accepted manuscript page[11]; PRF-02 page[6]
10 | FIG3-C | DEP-3C | deposit panel row | Panel_Data row 4 | 0.06 [0.01,0.14], R17 — matches controlling export. | VERIFY / NO CHANGE | Verify row and identity; retain values. | REPO-STEW | 2026-08-27T12:00:00+08:00 | Dependencies!A10:I10 | deposit_v3_manifest.xlsx ¦ Panel_Data!A4:H4; R17 Panel_Estimates!A5:M5
11 | FIG3-D | CAP-3D ¦ RS-3D | paired caption and results endpoints | AM pages 11 and 8; PRF pages 6 and 7 | Both endpoints match required order, unit, and no-marker semantics. | VERIFY BOTH / NO TEXT CHANGE | Conserve both distinct IDs; verify and retain both texts. | CA-STUDY | 2026-08-27T10:30:00+08:00 | Dependencies!A11:I11 | Accepted manuscript pages[8],[11]; PRF-02 pages[6],[7]
12 | FIG3-D | DEP-3D | deposit panel row | Panel_Data row 5 | 0.02 [-0.04,0.08], R17 — matches controlling export. | VERIFY / NO CHANGE | Verify row and identity; retain values. | REPO-STEW | 2026-08-27T12:00:00+08:00 | Dependencies!A12:I12 | deposit_v3_manifest.xlsx ¦ Panel_Data!A5:H5; R17 Panel_Estimates!A6:M6

## Actions
EXECUTABLE SINGLE-OWNER ACTION PLAN — ALL TIMES PRECEDE RE-REVIEW AND LOCK
Action ID | Panel / component | Action class | Executable action | Primary owner (exactly one) | Due time (Asia/Singapore) | Predecessor / acceptance evidence | Status at cutoff
ACT-B-EXPORT | FIG3-B | analysis confirmation | Confirm the approved R17 B row is 0.02 [-0.01,0.07] and provide it to production. | EMC-STAT | 2026-08-27T09:30:00+08:00 | R17 Panel_Estimates!A4:M4; author_correction_tracker.xlsx Owner_Routing!A4:E4 | OPEN
ACT-A-PROOF | FIG3-A | A/C proof fix | Correct legend pairing only: teal=Incentivized; amber=Non-incentivized. | PD-EDITOR | 2026-08-27T10:00:00+08:00 | Panel_Reconciliation FIG3-A; Owner_Routing!A2:E2 | OPEN
ACT-C-PROOF | FIG3-C | A/C proof fix | Restore visible annotation to n=42 from accepted baseline. | PD-EDITOR | 2026-08-27T10:00:00+08:00 | Panel_Reconciliation FIG3-C; Owner_Routing!A2:E2 | OPEN
ACT-D-VERIFY | FIG3-D | proof verification | Record D CLEAR and retain proof component unchanged. | PD-EDITOR | 2026-08-27T10:00:00+08:00 | Verification_Queue!A5:L5; Owner_Roles!A3:E3 | OPEN
ACT-CAP-3A | FIG3-A / CAP-3A | manuscript text approval | Verify/no text change after legend fix. | CA-STUDY | 2026-08-27T10:30:00+08:00 | Downstream_Impact CAP-3A; Owner_Routing!A5:E5 | OPEN
ACT-RS-3A | FIG3-A / RS-3A | manuscript text approval | Verify/no text change after legend fix. | CA-STUDY | 2026-08-27T10:30:00+08:00 | Downstream_Impact RS-3A; Owner_Routing!A5:E5 | OPEN
ACT-CAP-3B | FIG3-B / CAP-3B | manuscript text approval | Approve correction of upper endpoint to 0.07. | CA-STUDY | 2026-08-27T10:30:00+08:00 | Downstream_Impact CAP-3B; Owner_Routing!A5:E5 | OPEN
ACT-RS-3B | FIG3-B / RS-3B | manuscript text approval | Approve correction of upper endpoint to 0.07. | CA-STUDY | 2026-08-27T10:30:00+08:00 | Downstream_Impact RS-3B; Owner_Routing!A5:E5 | OPEN
ACT-SUP-F3 | FIG3-B / SUP-F3 | manuscript text approval | Approve printed label AR-2026-08-24-R17; retain R17 link. | CA-STUDY | 2026-08-27T10:30:00+08:00 | Downstream_Impact SUP-F3; Owner_Routing!A5:E5 | OPEN
ACT-CAP-3C | FIG3-C / CAP-3C | manuscript text approval | Verify/no text change after n=42 restoration. | CA-STUDY | 2026-08-27T10:30:00+08:00 | Downstream_Impact CAP-3C; Owner_Routing!A5:E5 | OPEN
ACT-D-TEXT | FIG3-D / CAP-3D + RS-3D | manuscript text approval | Verify both stable endpoint IDs; no text change. | CA-STUDY | 2026-08-27T10:30:00+08:00 | Downstream_Impact CAP-3D ¦ RS-3D; Owner_Routing!A5:E5 | OPEN
ACT-B-PROOF | FIG3-B | B proof regeneration | Regenerate B upper whisker from R17 to 0.07 after export confirmation. | PD-EDITOR | 2026-08-27T12:00:00+08:00 | ACT-B-EXPORT; Owner_Routing!A3:E3 | OPEN
ACT-README | DEP-README-COLOR | repository change | Correct exactly to teal=Incentivized and amber=Non-incentivized. | REPO-STEW | 2026-08-27T12:00:00+08:00 | Downstream_Impact DEP-README-COLOR; Owner_Routing!A6:E6 | OPEN
ACT-DEP-3B | DEP-3B | repository verification | Verify/no change numeric row and R17 identity. | REPO-STEW | 2026-08-27T12:00:00+08:00 | Downstream_Impact DEP-3B; Owner_Routing!A6:E6 | OPEN
ACT-DEP-3C | DEP-3C | repository verification | Verify/no change numeric row and R17 identity. | REPO-STEW | 2026-08-27T12:00:00+08:00 | Downstream_Impact DEP-3C; Owner_Routing!A6:E6 | OPEN
ACT-DEP-3D | DEP-3D | repository verification | Verify/no change numeric row and R17 identity. | REPO-STEW | 2026-08-27T12:00:00+08:00 | Downstream_Impact DEP-3D; Owner_Routing!A6:E6 | OPEN
ACT-PQL-REVIEW | PRF-02 + DEP-V3 / GATE-0147 | coupled re-review | Reinspect corrected pixels and mapped evidence; reapprove proof and release shared gate only if every prerequisite passes. | PQL | 2026-08-27T14:00:00+08:00 | All prior actions; deposit Release_Prerequisites!A2:F5; Owner_Routing!A7:E7 | OPEN

## Deposit_Gate
DEP-V3 LIFECYCLE AND COUPLED RELEASE CONTROL
Control field | Observed current state | Required release state | Disposition / action | Owner | Due | Precise public locator
Deposit identity | DEP-V3; HVD-EDU-0147; FIG3-EST-R17; AR-2026-08-24-R17; staged 2026-08-26T08:40:00+08:00; export SHA cd122e...01113. | Current R17 projection, exact export identity. | IDENTITY PASS. DEP-V3, not DEP-V2, is the staged projection. | REPO-STEW | 2026-08-27T12:00:00+08:00 | Workspace/06_Deposit/deposit_v3_manifest.xlsx ¦ File_Inventory!A2:I2; deposit_version_history.csv ¦ rows 2:3
Numeric rows | A-D Panel_Data values and R17 run IDs match the controlling export. | All mapped rows verified. | VALUES MATCH; verification prerequisite remains OPEN. | REPO-STEW | 2026-08-27T12:00:00+08:00 | deposit_v3_manifest.xlsx ¦ Panel_Data!A2:H5; R17 Panel_Estimates!A2:M6; Release_Prerequisites!A4:F4
Colour README | teal=Non-incentivized and amber=Incentivized. | teal=Incentivized and amber=Non-incentivized. | FAIL / CORRECT DEP-README-COLOR. | REPO-STEW | 2026-08-27T12:00:00+08:00 | deposit_v3_manifest.xlsx ¦ README_Entries!A2:E2; Release_Prerequisites!A3:F3
Linked proof reapproval | OPEN; PRF-02 contains unresolved A/B/C conditions. | Corrected proof reapproved. | BLOCKING OPEN prerequisite. | PQL | 2026-08-27T14:00:00+08:00 | deposit_v3_manifest.xlsx ¦ Release_Prerequisites!A2:F2; production_lock_schedule.md ¦ lines 24:26
Mapped rows verification | OPEN for DEP-3B, DEP-3C, DEP-3D. | All mapped deposit rows verified. | BLOCKING OPEN prerequisite. | REPO-STEW | 2026-08-27T12:00:00+08:00 | deposit_v3_manifest.xlsx ¦ Release_Prerequisites!A4:F4
Coupled gate | GATE-0147=QA_REVIEW_OPEN; proof=PRF-02; deposit=DEP-V3. | Gate releasable after final PQL review. | BLOCKING OPEN prerequisite; proof and deposit cannot receive contradictory states. | PQL | 2026-08-27T14:00:00+08:00 | production_lock_schedule.md ¦ lines 6:11, 24:26; deposit_v3_manifest.xlsx ¦ Release_Prerequisites!A5:F5
DEP-V3 disposition | Numerically synchronized, but README, linked-proof reapproval, mapped verification, and gate remain unresolved. | All four prerequisite classes complete. | HOLD_STAGED — DO NOT PUBLISH until README corrected, mapped rows verified, proof reapproved, and shared gate released. | PQL | 2026-08-27T14:00:00+08:00 | Rows above; publication_release_policy.pdf ¦ page[5]

## Source_Index
PUBLIC EVIDENCE INSPECTION INDEX — SOURCES, STRUCTURES, AND VISUAL ROUTES
Public file | Recomputed SHA-256 | Inspected structure / locator | Concrete observation used or bounded role
Workspace/00_Provenance/source_provenance.json | 4bc5cd5741de3afac479e6195fe3439f273c1ed86b29d37cb53039bf39f401a9 | /boundary; /sources[0:6] | Six source entries inspected. Boundary says authentic sources ground lifecycle/visual grammar/schemas/governance/metadata only and do not describe this case or disposition.
Workspace/01_Governance/accepted_submission_manifest.xlsx | ebcffa79ec9423c3640295cdd412009f6b56aec8a329953887eed332e06f61fc | Accepted_Set A1:H5; Version_History A1:G6; Proof_Events A1:H4; Checklist_History A1:J2; Owner_Roles A1:E7 | Accepted/approved identities, proof events, historical checklist, roles and deadlines inspected.
Workspace/01_Governance/late_replacement_approval_log.pdf | 80d9eb4af74d2ef118ef0c8954cc8526811b3f4f883dcf492e653a17581e229b | pages[1]-[4] | RR-017/A/B scope and matching hashes; CA/PQL approvals; LR3 null authority fields.
Workspace/01_Governance/publication_release_policy.pdf | 55c3e10fa8fbb36828cd106a0707896df1a1b1ab80efdd7fc26909228e83b2d6 | pages[1]-[6] | Centre rules inspected: cutoff/authority, all-dimensions tolerance, byte lineage, coupled HOLD precedence, owners/lock.
Workspace/02_Manuscript/accepted_manuscript_AM-2026-0147-v5.pdf | 58dd21c4f41658c8685861d5eee0c24fd728a2bfb644b82e71ad7bf2503e9935 | pages[1]-[12]; page[11].image[0] rendered and directly inspected | Accepted baseline image visibly shows C n=42 and D expected display; pages 8,10,11 hold mapped text.
Workspace/03_Analysis/analysis_environment_R17.json | e2a850c8aa68ab64f6bd02cf5ed9e7796f13df54ef79cbb695ceb277e8dec18d | all JSON fields | R17/output/input digests, package versions, publication_export approval, attestation time.
Workspace/03_Analysis/analysis_observations_R17.csv | 7381f1740a23ca4af11b780e78c003869d0590a990e5b984caa7c613555c018c | header row 1; rows 2:5281; all qc_flag/run fields recomputed | 5,280 records; 5,112 include; 168 exclude_predeclared; 5,280 unique keys; every row R17.
Workspace/03_Analysis/fig3_analysis_export_R17.xlsx | cd122e8b72c520eba3c8efa9f96799f3de579f9353cdb6712b337fe6f0c01113 | Run_Manifest A1:B11; Panel_Estimates A1:M6; Display_Map A1:H9; Cohort_Map A1:E3; QC_Summary A1:D5 | Controlling values, display map, run approval, input hash, and QC totals inspected.
Workspace/04_Proof/current_production_proof_PRF-02.pdf | 6ed5d5954db9225c97e69adba54f9196c7a162c2df060f5c0c3ae4b71c19b347 | pages[1]-[14]; page[6].image[0] rendered and directly inspected | Proof component pixels establish A reversed legend, B 0.11 upper whisker, C n=24, and D full pass; pages 6-7 hold current mapped text.
Workspace/04_Proof/figure3_current_proof_extracted.png | 779d11a0b97371edf7296b7818d83c8c5e93ac78da2a67f3b9b31c44e47106b5 | native 2400×1800; panel bounds from inventory; every panel directly inspected | Pixel-identical to PDF extraction (0 differing pixels); visual conclusions are recorded in panel and dimension sheets.
Workspace/04_Proof/figure3_registration_overlay.docx | 01e6255a56d93bdbd729a103673f0100d1214d78270471c8718c5d78755710a9 | paragraphs; table[1] rows 1:5; word/media/image1.png rendered/inspected | Registration-only artifact: x/y offset and dimensions reconcile to inventory; it explicitly records no findings and is not used as a finding source.
Workspace/04_Proof/proof_component_inventory.json | 37935fee856324fd7abb3169514834e851ffee2afcb9c5ab27d3e0347ae5698c | /proof; /figure_components/FIG3; /attachment_history | Proof/image identity, native bounds/calibration, LR2 links, and LR3 null links inspected.
Workspace/05_Dependencies/panel_content_dependency_map.xlsx | 4b2cbb8d98df68583d2064f5761497c2df448688b493fd6d45f57b43db43f788 | Dependencies!A1:I12 | Exactly 11 physical dependency rows and 12 stable endpoint IDs including paired CAP-3D ¦ RS-3D.
Workspace/06_Deposit/deposit_v3_manifest.xlsx | b0e4bfd22e1fb7e94698e0cb1d88b6379f8d47ff3b7b2d1d2dc87e83f59d6c15 | File_Inventory A1:I2; Panel_Data A1:H5; README_Entries A1:E2; Release_Prerequisites A1:F5 | V3 identity/numeric sync, reversed README colour key, and four open prerequisite classes.
Workspace/06_Deposit/deposit_version_history.csv | a8c620f06886555a6ac3d0a3ce38ad4a586bfc089bb5048e1e22ee35d2b72dc6 | header row 1; rows 2:3 | V2 public predecessor points to V3; V3 staged/unreleased; rollback fields null.
Workspace/07_Release_Control/author_correction_tracker.xlsx | e672950b09db088b9b69dd06f1db66bfe9b026c0c831eec665466f5247d82ebf | Verification_Queue A1:L18; Owner_Routing A1:E7 | All panel/dependency work units and exact single-owner routing/deadlines inspected.
Workspace/07_Release_Control/production_lock_schedule.md | a143157c290f4e78921fa69d82ea87481aa8947da323807aa18196c997bbe3a3 | lines 1:26 | Cutoff, QA_REVIEW_OPEN, linked PRF-02/DEP-V3, lock, schedule, and open prerequisites inspected.