# Figure 3 publication release memo

FINAL CONTROL DECISION  ·  AS OF 2026-08-26T17:00:00+08:00 (ASIA/SINGAPORE)

| To | Context |
| --- | --- |
| Centre Director; Corresponding Author (CA-STUDY); Production Editor (PD-EDITOR) | Final publication-consistency review of current proof PRF-02 and linked staged deposit DEP-V3 under GATE-0147. Production lock: 2026-08-28T18:00:00+08:00. |

# Decision

HOLD_CURRENT_PROOF_AND_LINKED_DEPOSIT — do not release PRF-02 and do not publish DEP-V3 as they stand.

Why this is a hold now. Three mandatory proof conditions remain unresolved (A, B and C), the staged README is unsynchronized, mapped verification and linked-proof reapproval remain open, and the shared gate has not been released. Under the centre’s precedence rule, any one of these conditions blocks both linked components; the proof and deposit cannot receive contradictory states. [Workspace/01_Governance/publication_release_policy.pdf, page[5]; Workspace/06_Deposit/deposit_v3_manifest.xlsx, Release_Prerequisites!A2:F5; Workspace/07_Release_Control/production_lock_schedule.md, lines 6:11 and 24:26]

Trigger and scope. The production alert at 2026-08-26T09:30:00+08:00 concerned cohort labels and uncertainty whiskers and triggered a publication-consistency review—not a scientific-merit inquiry. [Workspace/01_Governance/accepted_submission_manifest.xlsx, Proof_Events!A2:H2]

# Panel conclusions

| Panel | Observable business conclusion | Disposition | Owner / due (27 Aug, +08:00) |
| --- | --- | --- | --- |
| A | FIG3-LR2 authorized for A. Direct inspection of the proof image shows teal paired with Non-incentivized and amber with Incentivized; R17 requires teal=Incentivized and amber=Non-incentivized. Both visible estimates and intervals otherwise agree. | CORRECT_PROOF_LEGEND | PD-EDITOR · 2026-08-27 10:00 +08:00 |
| B | FIG3-LR2 authorized for B. The calibrated proof whisker reads 0.02 [-0.01, 0.11] against R17 0.02 [-0.01, 0.07]. The +0.04 upper-endpoint variance fails the centre’s inclusive 0.005 and one-pixel limits. | CORRECT_PROOF_AND_LINKED_TEXT | EMC-STAT · 2026-08-27 09:30; PD-EDITOR · 12:00 +08:00 |
| C | FIG3-ACC-v5 controls C because C was never requested or approved. Proof pixels visibly say n=24, while the accepted image and R17 require n=42; the estimate and interval pass. | REVERT_TO_ACCEPTED_ANNOTATION | PD-EDITOR · 2026-08-27 10:00 +08:00 |
| D | FIG3-ACC-v5 controls D. Direct inspection verifies 0.02 [-0.04, 0.08], Standardized Δz, 95% interval label, Incentivized-then-Non-incentivized order, required labels, and no exploratory marker. | CLEAR · RETAIN UNCHANGED | PD-EDITOR records check · 2026-08-27 10:00 +08:00 |

Visual evidence. All four findings above are grounded in direct inspection of Workspace/04_Proof/current_production_proof_PRF-02.pdf, page[6].image[0], and the pixel-identical native extraction Workspace/04_Proof/figure3_current_proof_extracted.png (2400×1800; panel bounds A [80,90,1190,870], B [1210,90,2320,870], C [80,930,1190,1710], D [1210,930,2320,1710]). C’s accepted comparison was directly inspected at Workspace/02_Manuscript/accepted_manuscript_AM-2026-0147-v5.pdf, page[11].image[0]. Structured comparisons use Workspace/03_Analysis/fig3_analysis_export_R17.xlsx, Panel_Estimates!A2:M6 and Display_Map!A2:H9. Exact approval scope is at Workspace/01_Governance/late_replacement_approval_log.pdf, pages[1]-[3].

# Deposit and downstream synchronization

DEP-V3 is the staged R17 projection, not DEP-V2. Its file inventory names FIG3-EST-R17 / AR-2026-08-24-R17 with the byte-matching export digest, and its numeric panel rows match R17. It remains HOLD_STAGED because DEP-README-COLOR currently reverses the colour key, mapped rows are not verified, the corrected proof is not reapproved, and GATE-0147 remains open. Correct the README exactly to “teal=Incentivized and amber=Non-incentivized”; verify DEP-3B, DEP-3C and DEP-3D; then obtain proof reapproval and shared-gate release. [Workspace/06_Deposit/deposit_v3_manifest.xlsx, File_Inventory!A2:I2, Panel_Data!A2:H5, README_Entries!A2:E2, Release_Prerequisites!A2:F5; Workspace/06_Deposit/deposit_version_history.csv, rows 2:3]

Mapped manuscript outcomes. CAP-3A and RS-3A are verify/no-change; CAP-3B and RS-3B change the upper endpoint to 0.07; SUP-F3 changes its printed run label to AR-2026-08-24-R17 while retaining the existing R17 link; CAP-3C is verify/no-change; CAP-3D and RS-3D are both conserved as verify/no-change. The complete 11-row / 12-endpoint accounting is in the register, Downstream_Impact!A2:L13. [Workspace/05_Dependencies/panel_content_dependency_map.xlsx, Dependencies!A2:I12]

# Executable sequence before any later release

| Primary owner | Due (Asia/Singapore, +08:00) | Required completion |
| --- | --- | --- |
| EMC-STAT | 2026-08-27 09:30 | Confirm the R17 B export row 0.02 [-0.01,0.07]. |
| PD-EDITOR | 2026-08-27 10:00 | Correct A legend; restore C to n=42; record D no-change verification. |
| CA-STUDY | 2026-08-27 10:30 | Approve CAP-3B/RS-3B at 0.07 and SUP-F3 at R17; complete mapped manuscript no-change checks. |
| PD-EDITOR | 2026-08-27 12:00 | Regenerate B from confirmed R17 and provide corrected proof. |
| REPO-STEW | 2026-08-27 12:00 | Correct DEP-README-COLOR and complete all mapped deposit-row verifications. |
| PQL | 2026-08-27 14:00 | Reinspect corrected proof, confirm all mapped evidence, reapprove PRF-02, and release the coupled gate only if every prerequisite passes. |

All deadlines precede the 2026-08-28T18:00:00+08:00 production lock. If any prerequisite remains open at the PQL re-review, maintain the hold and escalate under the lock schedule. Completion of the listed work permits a new coupled decision; it does not retroactively convert today’s hold into a release. [Workspace/07_Release_Control/author_correction_tracker.xlsx, Owner_Routing!A2:E7; Workspace/07_Release_Control/production_lock_schedule.md, lines 11:26]

# Evidence and scope boundary

Detailed evidence, hashes, pixel locators, authority history, endpoint allocation, and action rows are in figure3_reconciliation_register.xlsx: Decision!A3:D18; Panel_Reconciliation!A2:O6; Dimension_Checks!A2:J24; Evidence_Lineage!A2:I10; Authority_History!A2:G9; Downstream_Impact!A2:L13; Actions!A2:H19; Deposit_Gate!A2:G9.

Scope limitation. This memo concludes only on version authority, proof-to-data display consistency, downstream synchronization, and operational release control. The display tolerance and HOLD precedence are centre rules. The public-source provenance file expressly limits authentic sources to lifecycle, visual grammar, schema, governance and metadata grounding; no authentic source describes this case or its terminal decision. No conclusion is offered on scientific merit, causal validity, misconduct, or substantive educational effect. [Workspace/00_Provenance/source_provenance.json, /boundary; Workspace/01_Governance/publication_release_policy.pdf, pages[3] and [5]]