## 1_Review_Summary
Figure 3 publication-consistency review — summary
Case | CASE-EMC-2026-0147
Register | deliverables/figure3_reconciliation_register.xlsx
Companion memo | deliverables/publication_release_memo.docx
Evidence cutoff | 2026-08-26T17:00:00+08:00 (all retained events at or before this time)
Timezone | Asia/Singapore
Controlling policy | Publication Release Control SOP 4.2 (EFFECTIVE from 2026-07-01T00:00:00+08:00)
Coupled gate | GATE-0147 — proof PRF-02 + staged deposit DEP-V3 (one shared gate)
Gate state at review start | QA_REVIEW_OPEN
DECISION — coupled terminal state | RELEASE_AFTER_CORRECTIONS
Plain-language decision | Do not release now. Release the proof and the staged deposit together, and only after eight mandatory corrections are made and verified by PQL. If the FIG3-C authorization item (R-04) is still open at the coupled re-review, the gate escalates to HOLD.
PQL coupled re-review | 2026-08-27T14:00:00+08:00
Escalation to centre director | 2026-08-27T14:30:00+08:00 if any prerequisite remains open
Production lock | 2026-08-28T18:00:00+08:00 — all action due times precede this lock
Panels reviewed | 4 of 4 (FIG3-A, FIG3-B, FIG3-C, FIG3-D)
Register rows | 19 — 5 panel rows, 11 linked-endpoint rows, 1 gate row, 2 authorization rows
Mandatory corrections | 8 — R-01, R-02, R-03, R-04, R-08, R-09, R-10, R-11
Clear findings | 10 — R-05, R-06, R-07, R-12, R-13, R-14, R-15, R-16, R-17 (conforming) plus R-19 (not controlling)
Tolerance applied | <= 0.005 (two-decimal marks and geometry); geometry also <= 1 rendered px; 1 rendered px = 0.00038961 axis units at the calibrated scale
Hash verification | 5 of 5 asserted file-identity links recomputed and MATCH (sheet 6)
Scope limit | Production consistency, authorization and release-gate control only. This review makes no scientific-merit and no causal claim about any estimate, and does not reinterpret the study.

## 2_Reconciliation_Register
Ref | Row type | Panel | Mapped endpoint | What is visibly displayed (proof / staged deposit) | Controlling expected value or label | Variance against documented tolerance | Controlling version and approval state | Disposition | Downstream impact | Required action | Owner | Due (Asia/Singapore) | Visual locator (file + page + figure) | Structured-data locator (sheet + cell / row / record) | Effective rule applied
R-01 | Panel | FIG3-A | FIG3-A (panel) | Two horizontal interval series. Legend slot 1 = teal #148c8c swatch labelled "Non-incentivized"; slot 2 = amber #d98b1e swatch labelled "Incentivized". Teal series median +0.0399, endpoints -0.0203 / +0.1001. Amber series median -0.0100, endpoints -0.0702 / +0.0502. Axis -0.10:0.20 step 0.05; axis label "Standardized Δz"; interval label "95% interval". | Legend cohort 1 = "Incentivized", swatch 148C8C, order 1; legend cohort 2 = "Non-incentivized", swatch D98B1E, order 2. Incentivized 0.04 (-0.02, 0.10); Non-incentivized -0.01 (-0.07, 0.05). | LABEL FAIL (non-numeric, no tolerance allowance): the two cohort label texts are transposed relative to their swatches. Colour-to-value binding PASSES — teal #148c8c carries the Incentivized estimates and amber #d98b1e the Non-incentivized estimates, matching Display_Map. Geometry PASSES: max deviation 0.8 rendered px = 0.0003 axis units (limit 1 px and 0.005). Unit and interval label PASS. | Controlling display spec: FIG3-EST-R17 (approved publication export, 2026-08-25T16:00). Controlling component: FIG3-LR2, in RR-017 requested scope; CA approval APPR-RR017-CA and PQL approval APPR-RR017-PQL both record FIG3-A=approved. Component is AUTHORIZED; the defect is a build error inside approved scope. | FAIL — mandatory correction | CAP-3A and DEP-README-COLOR both describe this legend binding; RS-3A defers to the caption mapping. Blocks PREREQ-PROOF and the coupled gate. | Rebuild the FIG3-A legend so the 148C8C swatch reads "Incentivized" (order 1) and the D98B1E swatch reads "Non-incentivized" (order 2). Do not move the series geometry, which already conforms. | PD-EDITOR | 2026-08-27T10:00:00+08:00 | current_production_proof_PRF-02.pdf p.6, Figure 3 panel A legend (page[6].image[0], px x315-700 y810-900); figure3_current_proof_extracted.png same region | fig3_analysis_export_R17.xlsx Display_Map!A2:E3 (C2 "Incentivized"/D2 148C8C; C3 "Non-incentivized"/D3 D98B1E); Panel_Estimates!C2:F3 | SOP-4.2 §2 (labels and colour must agree; a matching median does not cure a failed label)
R-02 | Panel | FIG3-B | FIG3-B (panel) | Single teal #148c8c interval series. Median +0.0200; lower endpoint -0.0102; UPPER ENDPOINT +0.1102 (cap centre at px x1969.5). Axis -0.10:0.20 step 0.05; axis label "Standardized Δz"; interval label "95% interval". | Median 0.02; lower_95 -0.01; upper_95 0.07 (upper cap centre would fall at px x1866.3). | UPPER ENDPOINT FAIL. Deviation +0.0402 axis units / +103.2 rendered px against a limit of 0.005 axis units and 1 rendered px — exceeds tolerance by roughly 8x in axis units and 103x in pixels. Median PASSES (0.0 px) and lower endpoint PASSES (0.5 px); per SOP-4.2 §2 a matching median does not cure a failed endpoint. Unit and interval label PASS. | Controlling expected value: FIG3-EST-R17 Panel_Estimates!F4 = 0.07. Controlling component FIG3-LR2 is in RR-017 scope and approved for FIG3-B by both APPR-RR017-CA and APPR-RR017-PQL. Component AUTHORIZED; value is wrong. SUPERSEDED CONTEXT ONLY: the accepted baseline FIG3-ACC-v5 rendered this upper endpoint at 0.05 (AM p.11) — that is not the controlling target and 0.11 matches neither 0.07 nor 0.05. | FAIL — mandatory correction | CAP-3B (proof p.6) and RS-3B (proof p.7) both echo the erroneous 0.11. Deposit row DEP-3B independently carries the correct 0.07, so the deposit and the proof currently disagree. Blocks PREREQ-PROOF, PREREQ-ROWS and the coupled gate. | Regenerate FIG3-B from FIG3-EST-R17 so the upper interval endpoint renders at 0.07 within 1 rendered px, then re-extract and re-register the panel. | PD-EDITOR | 2026-08-27T12:00:00+08:00 | current_production_proof_PRF-02.pdf p.6, Figure 3 panel B upper whisker cap (page[6].image[0], px x1969.5 y437-473); figure3_current_proof_extracted.png same region | fig3_analysis_export_R17.xlsx Panel_Estimates!A4 row (D4=0.02, E4=-0.01, F4=0.07); Display_Map!A4:H4 (interval geometry, both endpoints, mandatory) | SOP-4.2 §2 (both uncertainty endpoints; ≤0.005 axis units and ≤1 rendered px)
R-03 | Panel | FIG3-C | FIG3-C (panel) — displayed annotation | Single teal #148c8c interval series with bold sample annotation "n=24" above the interval. Median +0.0601; endpoints +0.0097 / +0.1402. Axis label "Standardized Δz"; interval label "95% interval". | Sample annotation exactly "n=42". Median 0.06; lower_95 0.01; upper_95 0.14. | ANNOTATION FAIL (exact-text dimension, no tolerance allowance): "n=24" displayed where "n=42" is required — the digits are transposed. Geometry PASSES: max deviation 0.8 rendered px = 0.0003 axis units. Unit and interval label PASS. | Controlling expected value: FIG3-EST-R17 Panel_Estimates!L5 = "n=42" and Display_Map!C5 = "n=42" (mandatory, "exact annotation"). The accepted baseline FIG3-ACC-v5 also rendered "n=42" (AM p.11), so both the accepted and the approved states agree on n=42 and the proof departs from both. | FAIL — mandatory correction | CAP-3C (proof p.6) correctly states n=42, so the figure now contradicts its own caption on the same page. Blocks PREREQ-PROOF and the coupled gate. | Restore the FIG3-C sample annotation to exactly "n=42". Resolve jointly with R-04, which governs whether any change to FIG3-C may stand at all. | PD-EDITOR | 2026-08-27T10:00:00+08:00 | current_production_proof_PRF-02.pdf p.6, Figure 3 panel C annotation (page[6].image[0], px x694-732 y1216-1237); figure3_current_proof_extracted.png same region | fig3_analysis_export_R17.xlsx Panel_Estimates!L5 = "n=42"; Display_Map!A5:H5 (sample annotation, mandatory, exact annotation) | SOP-4.2 §2 (annotation must agree; exact text)
R-04 | Authorization | FIG3-C | FIG3-C — component authority / approved replacement scope | The FIG3-C region of the current proof rendition differs from the accepted baseline rendition: 506 changed pixels confined to the annotation area (px x694-732 y1216-1237). All other FIG3-C pixels are unchanged. So FIG3-C was materially altered by the FIG3-LR2 replacement. | No change to FIG3-C. RR-017 requested scope is exactly "FIG3-A, FIG3-B"; both approval scope matrices record FIG3-C = "not requested / not approved". | AUTHORIZATION FAIL. Under SOP-4.2 §1 an accepted component is superseded only when the exact replacement hash is proof-linked AND the request, corresponding-author approval and PQL approval all name that component. The hash is proof-linked and recomputes correctly, but no RR-017 instrument names FIG3-C. Hash equality proves identity and never expands approval scope (§3). The altered FIG3-C content is therefore an unapproved changed component. | Request RR-017 (2026-08-26T08:55) scope: FIG3-A, FIG3-B only. APPR-RR017-CA (10:40) and APPR-RR017-PQL (12:20): FIG3-C = not requested / not approved. Accepted baseline FIG3-ACC-v5 (2026-08-19T15:10) remains the authorized state for FIG3-C, and it carries "n=42". No rollback or invalidation event exists (Version_History!F2:F6 and deposit_version_history rollback_event_id all null). | FAIL — unapproved changed component; mandatory authorization remedy | This is an independent blocker from R-03: even once "n=42" is restored, the changed FIG3-C content needs authority. Blocks PREREQ-PROOF, PREREQ-GATE and the coupled gate. If unresolved at PQL re-review the gate must escalate to HOLD. | Either (a) restore FIG3-C to the authorized FIG3-ACC-v5 rendering so no unapproved change remains, or (b) raise a scoped replacement request naming FIG3-C and obtain corresponding-author and PQL approval for that scope. Record the chosen route in the approval log before coupled re-review. | PQL | 2026-08-27T14:00:00+08:00 | current_production_proof_PRF-02.pdf p.6 panel C vs accepted_manuscript_AM-2026-0147-v5.pdf p.11 panel C (both page[*].image[0]) | late_replacement_approval_log.pdf p.1 (requested scope), p.2 (CA scope matrix), p.3 (PQL scope matrix); proof_component_inventory.json attachment_history.FIG3-LR2; accepted_submission_manifest.xlsx Accepted_Set!A3:H3, Version_History!A4:G4 | SOP-4.2 §1 (component-scope supersession test), §3 (hash equality does not expand approval scope), §4 (unapproved changed component blocks both components)
R-05 | Panel | FIG3-D | FIG3-D (panel) | Single teal #148c8c interval series. Median +0.0200; endpoints -0.0402 / +0.0802. Category footnote reads "Incentivized" then "Non-incentivized" left to right. No exploratory marker present. Axis label "Standardized Δz"; interval label "95% interval"; axis -0.10:0.20 step 0.05. | Median 0.02; lower_95 -0.04; upper_95 0.08. Category order "Incentivized then Non-incentivized" (order 1 then 2). Exploratory marker = false (absence mandatory). | PASS on every dimension. Geometry max deviation 0.5 rendered px = 0.0002 axis units (limits 1 px / 0.005). Category order matches. Exploratory-marker absence confirmed: zero saturated non-teal, non-amber pixels anywhere in the panel. Unit and interval label exact. The FIG3-D region is pixel-identical to the accepted baseline (0 changed pixels), so no unapproved change exists here. | Controlling expected values: FIG3-EST-R17 Panel_Estimates!A6 row and Display_Map!A6:A7. FIG3-D is outside RR-017 scope and recorded as "not requested / not approved", but it is also unchanged, so the accepted baseline FIG3-ACC-v5 remains intact and authorized for this panel. | CLEAR — conforming; no correction required | CAP-3D ¦ RS-3D and DEP-3D all conform. Contributes no blocker to the coupled gate. | No corrective action. Confirm as clear at coupled re-review and close T-D-PANEL. | PD-EDITOR | 2026-08-27T10:00:00+08:00 | current_production_proof_PRF-02.pdf p.6, Figure 3 panel D (page[6].image[0], px 1210,930-2320,1710) | fig3_analysis_export_R17.xlsx Panel_Estimates!A6:M6 (D6=0.02, E6=-0.04, F6=0.08); Display_Map!A6:H7 | SOP-4.2 §2 (all dimensions incl. order and mandatory absence of exploratory marker)
R-06 | Caption clause | FIG3-A | CAP-3A | "CAP-3A: teal=Incentivized and amber=Non-incentivized." | teal (148C8C) = Incentivized; amber (D98B1E) = Non-incentivized — per Display_Map!C2/D2 and C3/D3. | PASS as written. The caption states the correct colour-to-cohort binding and matches the colour-to-value binding actually plotted. The defect is in the panel legend text (R-01), which now contradicts this correct caption. | Controlling wording source AM-2026-0147-v5 (accepted, 2026-08-19T15:10); the accepted caption at AM p.11 carries identical text. Controlling display spec FIG3-EST-R17. | CLEAR — no wording change; retained as the correct reference for the R-01 fix | Becomes consistent with the figure once R-01 is applied. No independent blocker. | No wording change. CA-STUDY to confirm the clause still reads correctly against the rebuilt legend and close T-CAP-3A. | CA-STUDY | 2026-08-27T10:30:00+08:00 | current_production_proof_PRF-02.pdf p.6 caption line 1; accepted baseline at accepted_manuscript_AM-2026-0147-v5.pdf p.11 caption line 1 | panel_content_dependency_map.xlsx Dependencies!A2:I2 (CAP-3A, display semantics, AM page 11; PRF page 6); author_correction_tracker.xlsx Verification_Queue!A7:L7 | SOP-4.2 §2 (cohort label and colour agreement)
R-07 | Results statement | FIG3-A | RS-3A | "RS-3A: The incentive-condition comparison follows the cohort mapping stated in the caption." (proof p.7) | Accepted wording: "The incentive-condition comparison is interpreted using the cohort mapping stated in the Figure 3 caption." (AM p.8). Substantively identical deferral to the caption; no independent numeric or label claim. | PASS. The statement makes no independent estimate, endpoint, label or colour claim, so it introduces no variance of its own. It inherits correctness from CAP-3A (clear, R-06). Wording differs only in phrasing from the accepted text and asserts nothing further. | Controlling wording source AM-2026-0147-v5 (accepted). No approval instrument changes results prose; RR-017 is a figure-component request only. | CLEAR — no correction required | No downstream impact once R-01 is applied. No independent blocker. | No change. CA-STUDY to confirm against the rebuilt legend and close T-RS-3A. | CA-STUDY | 2026-08-27T10:30:00+08:00 | current_production_proof_PRF-02.pdf p.7 line 1 ("Results: Figure 3"); accepted wording at accepted_manuscript_AM-2026-0147-v5.pdf p.8 line 1 | panel_content_dependency_map.xlsx Dependencies!A3:I3 (RS-3A, interpretive echo, AM page 8; PRF page 7); author_correction_tracker.xlsx Verification_Queue!A8:L8 | SOP-4.2 §2 (label/cohort agreement across mapped endpoints)
R-08 | Deposit README entry | FIG3-A | DEP-README-COLOR | figure3_colour_key = "teal=Non-incentivized and amber=Incentivized" (state: staged text) | "teal=Incentivized and amber=Non-incentivized" — per Display_Map!C2/D2 and C3/D3, and matching CAP-3A. | COLOUR-TO-COHORT FAIL (exact-text dimension, no tolerance allowance): the staged README key transposes the two cohort names against the controlling display map and against the proof caption CAP-3A. This is the same transposition defect as the proof legend (R-01) reproduced independently in the deposit. | Controlling display spec FIG3-EST-R17 (approved 2026-08-25T16:00), whose bytes are the staged deposit file (hash cd122e…1113 recomputed, MATCH). Deposit DEP-V3 is staged / unreleased; its predecessor DEP-V2 is public but is superseded context (successor DEP-V3, rollback_event_id null) and does not control. | FAIL — mandatory correction before deposit release | Directly blocks PREREQ-README. A released deposit README would contradict the published caption. Blocks the coupled gate; DEP-V3 may not release ahead of the proof (proof p.11). | Correct the staged README entry to "teal=Incentivized and amber=Non-incentivized" and re-verify it against Display_Map before the coupled re-review. | REPO-STEW | 2026-08-27T12:00:00+08:00 | cross-check against current_production_proof_PRF-02.pdf p.6 caption line 1 and the panel A legend at page[6].image[0] px x315-700 y810-900 | deposit_v3_manifest.xlsx README_Entries!D2 (item DEP-README-COLOR, row 2); expected at fig3_analysis_export_R17.xlsx Display_Map!C2:D3; Release_Prerequisites!A3:F3; Verification_Queue!A9:L9 | SOP-4.2 §2 (cohort label and colour agreement), §4 (unsynchronized mapped deposit item blocks both linked components)
R-09 | Caption clause | FIG3-B | CAP-3B | "CAP-3B: the overall 95% interval extends to 0.11." (proof p.6) | Upper endpoint 0.07 per FIG3-EST-R17 Panel_Estimates!F4. | NUMERIC FAIL. ¦0.11 - round-half-up(0.07, 2)¦ = 0.040 against a limit of 0.005 — exceeds tolerance by 8x. The caption echoes the same wrong endpoint that the panel renders (R-02). | Controlling value FIG3-EST-R17 Panel_Estimates!F4 = 0.07. SUPERSEDED CONTEXT ONLY: the accepted caption at AM p.11 read "accepted interval endpoint is 0.05"; that state is superseded by the approved R17 export and 0.11 matches neither. Dependency source_version for CAP-3B is PRF-02 (numeric echo). | FAIL — mandatory correction | Blocks PREREQ-PROOF and the coupled gate; must be corrected in step with R-02 and R-10 so all three state 0.07. | Amend the caption clause to state the 0.07 upper endpoint, matching the regenerated panel and FIG3-EST-R17. | CA-STUDY | 2026-08-27T10:30:00+08:00 | current_production_proof_PRF-02.pdf p.6 caption line 1 ("CAP-3B: the overall 95% interval extends to 0.11"); superseded accepted text at accepted_manuscript_AM-2026-0147-v5.pdf p.11 caption | fig3_analysis_export_R17.xlsx Panel_Estimates!F4 = 0.07; panel_content_dependency_map.xlsx Dependencies!A5:I5 (CAP-3B, numeric echo, PRF page 6); Verification_Queue!A10:L10 | SOP-4.2 §2 (two-decimal mark tolerance ≤0.005 vs round-half-up(source,2))
R-10 | Results statement | FIG3-B | RS-3B | "RS-3B: The overall interval extends to 0.11 in the current production wording." (proof p.7) | Upper endpoint 0.07 per FIG3-EST-R17 Panel_Estimates!F4. | NUMERIC FAIL. ¦0.11 - 0.07¦ = 0.040 against a limit of 0.005 — exceeds tolerance by 8x. Third independent surface carrying the same wrong endpoint. | Controlling value FIG3-EST-R17 Panel_Estimates!F4 = 0.07. SUPERSEDED CONTEXT ONLY: accepted RS-3B at AM p.8 read "extends from -0.02 to 0.05"; superseded by the approved R17 export, and 0.11 matches neither state. Dependency source_version PRF-02. | FAIL — mandatory correction | Blocks PREREQ-PROOF and the coupled gate; correct in step with R-02 and R-09. | Amend the results statement to the 0.07 upper endpoint, consistent with the regenerated panel and the corrected caption. | CA-STUDY | 2026-08-27T10:30:00+08:00 | current_production_proof_PRF-02.pdf p.7 line 2; superseded accepted text at accepted_manuscript_AM-2026-0147-v5.pdf p.8 line 2 | fig3_analysis_export_R17.xlsx Panel_Estimates!F4 = 0.07; panel_content_dependency_map.xlsx Dependencies!A6:I6 (RS-3B, numeric echo, PRF page 7); Verification_Queue!A11:L11 | SOP-4.2 §2 (two-decimal mark tolerance ≤0.005)
R-11 | Supplementary reference | FIG3-B | SUP-F3 | Printed run label "AR-2026-08-18-R16" (AM p.10). Proof p.10 states only that SUP-F3 remains linked by stable content identifier. Linked file hash field carries cd122e8b…c01113. | Printed run label should name the controlling approved run AR-2026-08-24-R17; linked file hash cd122e8b…c01113 (FIG3-EST-R17). | LABEL FAIL (stale run label) on the printed-label field only. The linked-file hash field PASSES: recomputed SHA-256 of fig3_analysis_export_R17.xlsx equals cd122e8b…c01113 exactly, matching Dependencies!H7 and the deposit inventory. The dependency map notes that printed label and linked file hash are separate fields, and here they diverge: the file is R17, the printed label still says R16. | Controlling run AR-2026-08-24-R17 (approved 2026-08-25T16:00, Version_History row 6). AR-2026-08-18-R16 is SUPERSEDED (Version_History!C5 = superseded, successor AR-2026-08-24-R17, rollback_event_id null), so the printed label points at superseded context. Hash equality confirms identity of the R17 file and does not cure the label. | FAIL — mandatory correction | Under ICMJE-grounded citation-to-latest-version and software/version disclosure principles the printed label must name the run actually deposited. Blocks PREREQ-PROOF and the coupled gate. | Update the printed supplementary run label to AR-2026-08-24-R17. No file replacement is required — the linked bytes are already the correct R17 export. | CA-STUDY | 2026-08-27T10:30:00+08:00 | accepted_manuscript_AM-2026-0147-v5.pdf p.10 "Supporting information" ("Printed run label: AR-2026-08-18-R16"); current_production_proof_PRF-02.pdf p.10 | panel_content_dependency_map.xlsx Dependencies!A7:I7 (SUP-F3, run label, AM page 10, H7 = cd122e8b…c01113); accepted_submission_manifest.xlsx Version_History!A5:G5 (R16 superseded) and A6:F6 (R17 approved); Run_Manifest!B2; Verification_Queue!A12:L12 | SOP-4.2 §1 (eligibility does not create authority), §3 (hash equality proves identity, never expands scope; prior versions are historical context)
R-12 | Deposit panel row | FIG3-B | DEP-3B | Panel_Data row 3: median 0.02; lower_95 -0.01; upper_95 0.07; unit "standardized delta-z"; analysis_run_id AR-2026-08-24-R17. | Median 0.02; lower_95 -0.01; upper_95 0.07; unit "standardized delta-z"; run AR-2026-08-24-R17 — per Panel_Estimates!A4 row. | PASS on all fields; all three numeric values agree exactly (deviation 0.000 against the 0.005 limit), unit and run label match. Note the deposit row is CORRECT while the proof panel and its caption/results echoes are wrong (R-02, R-09, R-10) — the deposit is the conforming side of that disagreement. | Controlling export FIG3-EST-R17; staged deposit file hash recomputed MATCH (cd122e8b…c01113). DEP-V3 staged / unreleased; DEP-V2 (R16) is superseded public context only. | CLEAR — row conforms; still gated by the coupled release | Supports PREREQ-ROWS. Cannot release independently: DEP-V3 is coupled to PRF-02 (proof p.11) and is held by the proof-side failures. | No data change. REPO-STEW to record the row as verified under PREREQ-ROWS and close T-DEP-3B; release only with the coupled gate. | REPO-STEW | 2026-08-27T12:00:00+08:00 | cross-check against current_production_proof_PRF-02.pdf p.6 panel B (page[6].image[0], px x1659-1971 y437-473) | deposit_v3_manifest.xlsx Panel_Data!A3:H3 (D3=0.02, E3=-0.01, F3=0.07); fig3_analysis_export_R17.xlsx Panel_Estimates!A4:M4; Dependencies!A8:I8; Release_Prerequisites!A4:F4; Verification_Queue!A13:L13 | SOP-4.2 §2 (estimate, endpoints, unit), §4 (coupled release)
R-13 | Caption clause | FIG3-C | CAP-3C | "CAP-3C: across-class annotation n=42." (proof p.6) | "n=42" per Display_Map!C5 and Panel_Estimates!L5. | PASS as written. The caption carries the correct annotation value. The defect is in the panel annotation (R-03), which now reads n=24 and contradicts this correct caption on the same printed page. | Controlling wording source AM-2026-0147-v5 (accepted); the accepted caption at AM p.11 carries identical text. Controlling display spec FIG3-EST-R17. | CLEAR — no wording change; retained as the correct reference for the R-03 fix | Becomes consistent with the figure once R-03 is applied. No independent blocker. | No wording change. CA-STUDY to confirm against the corrected annotation and close T-CAP-3C. | CA-STUDY | 2026-08-27T10:30:00+08:00 | current_production_proof_PRF-02.pdf p.6 caption line 1 ("CAP-3C: across-class annotation n=42"); accepted baseline at accepted_manuscript_AM-2026-0147-v5.pdf p.11 caption | fig3_analysis_export_R17.xlsx Display_Map!C5 = "n=42", Panel_Estimates!L5; panel_content_dependency_map.xlsx Dependencies!A9:I9 (CAP-3C, annotation semantics); Verification_Queue!A14:L14 | SOP-4.2 §2 (annotation agreement; exact text)
R-14 | Deposit panel row | FIG3-C | DEP-3C | Panel_Data row 4: median 0.06; lower_95 0.01; upper_95 0.14; unit "standardized delta-z"; analysis_run_id AR-2026-08-24-R17. | Median 0.06; lower_95 0.01; upper_95 0.14; unit "standardized delta-z"; run AR-2026-08-24-R17 — per Panel_Estimates!A5 row. | PASS on all fields; numeric deviation 0.000 against the 0.005 limit, unit and run label match. The deposit row carries no sample-size field, so the n=24/n=42 annotation defect (R-03) does not propagate here. | Controlling export FIG3-EST-R17; staged file hash recomputed MATCH. DEP-V3 staged / unreleased; DEP-V2 superseded public context only. | CLEAR — row conforms; still gated by the coupled release | Supports PREREQ-ROWS. Held by the coupled gate, not by any defect of its own. | No data change. REPO-STEW to record as verified under PREREQ-ROWS and close T-DEP-3C; release only with the coupled gate. | REPO-STEW | 2026-08-27T12:00:00+08:00 | cross-check against current_production_proof_PRF-02.pdf p.6 panel C (page[6].image[0], px x550-888 y1257-1293) | deposit_v3_manifest.xlsx Panel_Data!A4:H4 (D4=0.06, E4=0.01, F4=0.14); fig3_analysis_export_R17.xlsx Panel_Estimates!A5:M5; Dependencies!A10:I10; Release_Prerequisites!A4:F4; Verification_Queue!A15:L15 | SOP-4.2 §2 (estimate, endpoints, unit), §4 (coupled release)
R-15 | Paired caption + results | FIG3-D | CAP-3D ¦ RS-3D | CAP-3D (proof p.6): "Incentivized precedes Non-incentivized; no exploratory marker." RS-3D (proof p.7): "The moderator panel uses the pre-registered category order and standardized delta-z unit." Both endpoint IDs retained in this single physical register row per the dependency map's paired no-loss mapping. | Category order "Incentivized then Non-incentivized"; exploratory marker false (absence mandatory); unit "Standardized Δz" — per Display_Map!A6:A7 and C8. | PASS on both endpoints. CAP-3D states the correct order and correctly asserts absence of an exploratory marker, which the panel confirms (zero saturated non-teal/non-amber pixels). RS-3D asserts order and unit only, both of which hold. Accepted wording at AM p.8 and p.11 is substantively identical; no numeric claim is made by either endpoint. | Controlling wording source AM-2026-0147-v5 (accepted); controlling display spec FIG3-EST-R17. FIG3-D is outside RR-017 scope and is unchanged, so the accepted baseline remains authorized. | CLEAR — no correction required (both CAP-3D and RS-3D) | No downstream impact; contributes no blocker to the coupled gate. | No change. CA-STUDY to confirm and close both T-CAP-3D and T-RS-3D. | CA-STUDY | 2026-08-27T10:30:00+08:00 | current_production_proof_PRF-02.pdf p.6 caption line 2 (CAP-3D) and p.7 line 3 (RS-3D); accepted wording at accepted_manuscript_AM-2026-0147-v5.pdf p.11 and p.8; marker absence verified at page[6].image[0] px 1210,930-2320,1710 | fig3_analysis_export_R17.xlsx Display_Map!A6:H7 (category order; exploratory marker false) and C8 (unit); panel_content_dependency_map.xlsx Dependencies!A11:I11 (CAP-3D ¦ RS-3D, paired); Verification_Queue!A16:L16 and A17:L17 | SOP-4.2 §2 (order, unit, mandatory absence of annotation/marker)
R-16 | Deposit panel row | FIG3-D | DEP-3D | Panel_Data row 5: median 0.02; lower_95 -0.04; upper_95 0.08; unit "standardized delta-z"; analysis_run_id AR-2026-08-24-R17. | Median 0.02; lower_95 -0.04; upper_95 0.08; unit "standardized delta-z"; run AR-2026-08-24-R17 — per Panel_Estimates!A6 row. | PASS on all fields; numeric deviation 0.000 against the 0.005 limit, unit and run label match. | Controlling export FIG3-EST-R17; staged file hash recomputed MATCH. DEP-V3 staged / unreleased; DEP-V2 superseded public context only. | CLEAR — row conforms; still gated by the coupled release | Supports PREREQ-ROWS. Held by the coupled gate, not by any defect of its own. | No data change. REPO-STEW to record as verified under PREREQ-ROWS and close T-DEP-3D; release only with the coupled gate. | REPO-STEW | 2026-08-27T12:00:00+08:00 | cross-check against current_production_proof_PRF-02.pdf p.6 panel D (page[6].image[0], px x1582-1894 y1257-1293) | deposit_v3_manifest.xlsx Panel_Data!A5:H5 (D5=0.02, E5=-0.04, F5=0.08); fig3_analysis_export_R17.xlsx Panel_Estimates!A6:M6; Dependencies!A12:I12; Release_Prerequisites!A4:F4; Verification_Queue!A18:L18 | SOP-4.2 §2 (estimate, endpoints, unit), §4 (coupled release)
R-17 | Deposit entry | FIG3-A (mapped) / deposit-wide | DEP-V3 File_Inventory — DEP-3A-IMM row and staged file identity | File_Inventory row 2: FIG3-EST-R17 / fig3_analysis_export_R17.xlsx, file_uuid 0a7d5b4a-95e6-4ce1-b7a1-1db43a6cd017, sha256 cd122e8b…c01113, run AR-2026-08-24-R17, state "staged", staged_at 2026-08-26T08:40. Panel_Data row 2 (DEP-3A-IMM): Incentivized, median 0.04, -0.02, 0.10, standardized delta-z. | Staged file must be the approved R17 export bytes; DEP-3A-IMM must match Panel_Estimates!A2 row (Incentivized 0.04, -0.02, 0.10). | PASS on file identity and on the DEP-3A-IMM numeric row: recomputed SHA-256 equals cd122e8b…c01113 exactly, and all three estimates agree (deviation 0.000 vs the 0.005 limit) with the correct cohort name attached to the correct values. Note the deposit carries no Non-incentivized panel-A row, so the only FIG3-A cohort-labelling surface in the deposit is the README key, which fails (R-08). | DEP-V3 is staged / unreleased (deposit_version_history row 3, access_state "unreleased", successor blank, rollback null). DEP-V2 is "public predecessor" on the superseded R16 run — SUPERSEDED CONTEXT, not controlling and not a rollback target. Concept HVD-EDU-0147 spans both. | CLEAR on identity and data; HELD by the coupled gate | DEP-V3 cannot release independently of PRF-02 (proof p.11; SOP-4.2 §4). It is currently held by R-08 on its own README plus the proof-side failures. | No file replacement. Hold DEP-V3 unreleased until R-08 is corrected and the coupled gate clears; then publish only together with the corrected proof. | REPO-STEW | 2026-08-27T12:00:00+08:00 | cross-check against current_production_proof_PRF-02.pdf p.11 "Data availability" (staged version may not release independently) and p.6 panel A teal series | deposit_v3_manifest.xlsx File_Inventory!A2:I2 and Panel_Data!A2:H2; deposit_version_history.csv row 3 (DEP-V3 staged/unreleased) and row 2 (DEP-V2 superseded public predecessor); fig3_analysis_export_R17.xlsx Panel_Estimates!A2:M2 | SOP-4.2 §3 (hash lineage; prior versions are historical context), §4 (coupled release)
R-18 | Coupled release gate | All panels (gate-level) | GATE-0147 — coupled proof PRF-02 + deposit DEP-V3 | Current gate state QA_REVIEW_OPEN. All four Release_Prerequisites are "open" (PREREQ-PROOF, PREREQ-README, PREREQ-ROWS, PREREQ-GATE). All 17 Verification_Queue tasks are "open". No final release recommendation is recorded. | A single terminal state applied to both linked components, chosen from RELEASE, RELEASE_AFTER_CORRECTIONS or HOLD, with no contradictory terminal states across the proof and the deposit. | Eight mandatory corrections are unresolved: R-01 (FIG3-A legend labels), R-02 (FIG3-B upper endpoint, 0.040 over a 0.005 limit), R-03 (FIG3-C annotation n=24), R-04 (FIG3-C unapproved changed component), R-08 (deposit README colour key), R-09 and R-10 (caption and results echoes of the wrong 0.11 endpoint), R-11 (SUP-F3 stale run label R16). RELEASE is therefore unavailable. Every failure is diagnosed, has a named owner and a due time before the 2026-08-27T14:00 re-review, and each has a defined remedy inside the existing approval framework, so RELEASE_AFTER_CORRECTIONS is the applicable state rather than HOLD — provided R-04 is resolved by restoration or by a properly scoped new approval. If R-04 is still open at the coupled re-review, precedence under §4 escalates the gate to HOLD. | Gate authority: production_lock_schedule.md (GATE-0147, allowed terminal states, lock 2026-08-28T18:00) and SOP-4.2 §4 precedence HOLD > RELEASE_AFTER_CORRECTIONS > RELEASE. Coupled components PRF-02 and DEP-V3. All relied-on events carry parseable timestamps at or before the 2026-08-26T17:00 cutoff; FIG3-LR3 (received 16:40, eligible by time) confers no authority — see R-19. | RELEASE_AFTER_CORRECTIONS — do not release now; release both components together once all eight corrections are verified | Binds the proof and the deposit to one terminal state. No independent deposit release. Production lock 2026-08-28T18:00 remains achievable if all owner due times are met. | Hold both components unreleased. Complete R-01, R-02, R-03, R-04, R-08, R-09, R-10 and R-11 by their owner due times, then PQL to re-review the coupled gate and set the single terminal state; escalate to the centre director at 2026-08-27T14:30 if any prerequisite is still open. | PQL | 2026-08-27T14:00:00+08:00 | current_production_proof_PRF-02.pdf p.11 ("A staged version may not release independently of the production proof") and p.14 (proof pending open quality-review workflow) | production_lock_schedule.md lines 7-11 and 22-26; deposit_v3_manifest.xlsx Release_Prerequisites!A2:F5 (all "open"); author_correction_tracker.xlsx Verification_Queue!L2:L18 (all "open"); publication_release_policy.pdf p.5 | SOP-4.2 §4 (allowed states, precedence, no contradictory terminal states), §5 (owners and due times precede lock)
R-19 | Authorization | FIG3 (attachment-level) | FIG3-LR3 — unrequested late attachment | Attachment FIG3-LR3, filename Figure3_final_v9.png, received 2026-08-26T16:40, sha256 536e3d5c…89566. Request ID null; corresponding-author approval null; PQL approval null; proof component link null. Lifecycle state: orphan attachment, retained in history. The file itself is not present in the workspace, so no bytes were available to hash. | No display consequence. To control any panel it would need a request, corresponding-author approval and PQL approval all naming that component, plus a proof-linked hash. | NOT APPLICABLE to display comparison — correctly excluded. Its 16:40 timestamp is at or before the 17:00 cutoff, so it is time-eligible, but SOP-4.2 §1 states that eligibility does not create authority: with all four link fields null it supersedes nothing. FIG3-LR2 remains the controlling proof component. Recorded here so the exclusion is explicit rather than silent. | Controlling component remains FIG3-LR2 (proof-linked, hash recomputed MATCH, approved for FIG3-A and FIG3-B). FIG3-LR3 is an orphan attachment held as history only. | NOT CONTROLLING — excluded from the comparison; no action beyond record-keeping | None. Must not be substituted into the proof as a shortcut fix for R-01 through R-04; doing so would create a fresh unapproved changed component. | Leave unlinked. If any part of it is wanted, route it through a scoped replacement request with corresponding-author and PQL approval naming each affected panel before the coupled re-review. | PQL | 2026-08-27T14:00:00+08:00 | no visual locator — file absent from the workspace; recorded at late_replacement_approval_log.pdf p.4 "Attachment history" | proof_component_inventory.json attachment_history.FIG3-LR3 (request_id, author_approval_id, pql_approval_id, proof_component_link all null); late_replacement_approval_log.pdf p.4 | SOP-4.2 §1 (eligibility does not create authority; component-scope supersession test)

## 3_Panel_Dimension_Matrix
Panel | Identity | Cohort label | Colour | Category order | Median / estimate | Lower endpoint | Upper endpoint | Unit | Annotation | Authorization | Panel verdict
FIG3-A | PASS | FAIL | PASS | FAIL | PASS | PASS | PASS | PASS | n/a | PASS | FAIL — legend cohort labels transposed (R-01)
FIG3-B | PASS | PASS | PASS | n/a | PASS | PASS | FAIL | PASS | n/a | PASS | FAIL — upper endpoint 0.11 vs 0.07 (R-02)
FIG3-C | PASS | PASS | PASS | n/a | PASS | PASS | PASS | PASS | FAIL | FAIL | FAIL — annotation n=24 vs n=42 (R-03) and unapproved change (R-04)
FIG3-D | PASS | PASS | PASS | PASS | PASS | PASS | PASS | PASS | PASS (marker absent) | PASS | CLEAR — conforms on every dimension (R-05)
Reading notes
Colour PASS for FIG3-A means the colour-to-value binding is correct (teal #148c8c carries the Incentivized estimates). The FAIL is on the legend label text and its order, which are transposed against those swatches. Per SOP-4.2 §2 a correct median never cures a failed label or order.
"Authorization" tests the SOP-4.2 §1 component-scope rule: the request, the corresponding-author approval and the PQL approval must all name the panel. FIG3-C fails because its content changed while every RR-017 instrument records it as not requested / not approved.
"n/a" marks a dimension the controlling display map does not assert for that panel (for example no category-order requirement for the single-series panels B and C, and no mandated annotation for A, B or D).
FIG3-D is pixel-identical to the accepted baseline across the whole panel region, so it raises no authorization question even though it sits outside the RR-017 approved scope.

## 4_Geometry_Measurements
Panel | Series / mark | Measured (axis units) | Controlling source value | Source cell | Deviation (axis units) | Deviation (rendered px) | Within 0.005? | Within 1 px? | Verdict
FIG3-A | Incentivized (teal #148c8c) median | 0.0399 | 0.04 | Panel_Estimates!D2 | -0.0001 | -0.3 | YES | YES | PASS
FIG3-A | Incentivized lower endpoint | -0.0203 | -0.02 | Panel_Estimates!E2 | -0.0003 | -0.8 | YES | YES | PASS
FIG3-A | Incentivized upper endpoint | 0.1001 | 0.1 | Panel_Estimates!F2 | 0.0001 | 0.2 | YES | YES | PASS
FIG3-A | Non-incentivized (amber #d98b1e) median | -0.01 | -0.01 | Panel_Estimates!D3 | 0 | 0 | YES | YES | PASS
FIG3-A | Non-incentivized lower endpoint | -0.0702 | -0.07 | Panel_Estimates!E3 | -0.0002 | -0.5 | YES | YES | PASS
FIG3-A | Non-incentivized upper endpoint | 0.0502 | 0.05 | Panel_Estimates!F3 | 0.0002 | 0.5 | YES | YES | PASS
FIG3-B | Immediate minus Delayed median | 0.02 | 0.02 | Panel_Estimates!D4 | 0 | 0 | YES | YES | PASS
FIG3-B | lower endpoint | -0.0102 | -0.01 | Panel_Estimates!E4 | -0.0002 | -0.5 | YES | YES | PASS
FIG3-B | UPPER ENDPOINT | 0.1102 | 0.07 | Panel_Estimates!F4 | 0.0402 | 103.2 | NO | NO | FAIL — 8x the 0.005 axis limit and 103x the 1 px limit
FIG3-C | Across-class heterogeneity median | 0.0601 | 0.06 | Panel_Estimates!D5 | 0.0001 | 0.3 | YES | YES | PASS
FIG3-C | lower endpoint | 0.0097 | 0.01 | Panel_Estimates!E5 | -0.0003 | -0.8 | YES | YES | PASS
FIG3-C | upper endpoint | 0.1402 | 0.14 | Panel_Estimates!F5 | 0.0002 | 0.5 | YES | YES | PASS
FIG3-D | Pre-registered moderator median | 0.02 | 0.02 | Panel_Estimates!D6 | 0 | 0 | YES | YES | PASS
FIG3-D | lower endpoint | -0.0402 | -0.04 | Panel_Estimates!E6 | -0.0002 | -0.5 | YES | YES | PASS
FIG3-D | upper endpoint | 0.0802 | 0.08 | Panel_Estimates!F6 | 0.0002 | 0.5 | YES | YES | PASS
Method: the panel bounds and axis calibration in proof_component_inventory.json were applied to the embedded rendition at native 2400x1800 scale. Axis span -0.10 to 0.20 over 770 rendered px gives 1 px = 0.00038961 axis units, so the 0.005 axis tolerance is the binding constraint at about 12.8 px and the 1 px constraint is the tighter of the two.
The extracted PNG figure3_current_proof_extracted.png was confirmed pixel-identical to PRF-02 page[6].image[0], so visual and structured measurements refer to the same bytes.
Endpoint positions are measured at whisker-cap centres; medians at the point-marker centroid. Sub-pixel residuals under 1 px are rasterization noise, not display variance.
All source values equal their round-half-up two-decimal form, so no rounding step affects any comparison in this sheet.

## 5_Action_Plan
Ref | Panel / component | Mandatory correction | Required action | Owner | Due (Asia/Singapore) | Precedes PQL re-review? | Precedes production lock? | Blocks which prerequisite | Tracker task
R-01 | FIG3-A legend | YES | Rebuild the panel A legend so swatch 148C8C reads "Incentivized" (order 1) and D98B1E reads "Non-incentivized" (order 2); leave series geometry untouched. | PD-EDITOR | 2026-08-27T10:00:00+08:00 | YES — before 2026-08-27T14:00 | YES — before 2026-08-28T18:00 | PREREQ-PROOF | T-A-PANEL
R-02 | FIG3-B panel | YES | Regenerate panel B from FIG3-EST-R17 so the upper endpoint renders at 0.07 within 1 rendered px; re-extract and re-register. | PD-EDITOR | 2026-08-27T12:00:00+08:00 | YES — before 2026-08-27T14:00 | YES — before 2026-08-28T18:00 | PREREQ-PROOF | T-B-PANEL / T-B-EXPORT
R-03 | FIG3-C annotation | YES | Restore the sample annotation to exactly "n=42"; resolve jointly with R-04. | PD-EDITOR | 2026-08-27T10:00:00+08:00 | YES — before 2026-08-27T14:00 | YES — before 2026-08-28T18:00 | PREREQ-PROOF | T-C-PANEL
R-04 | FIG3-C authority | YES | Either restore FIG3-C to the authorized FIG3-ACC-v5 rendering, or obtain a scoped request plus corresponding-author and PQL approval naming FIG3-C. Record the route in the approval log. | PQL | 2026-08-27T14:00:00+08:00 | YES — before 2026-08-27T14:00 | YES — before 2026-08-28T18:00 | PREREQ-PROOF / PREREQ-GATE | T-C-PANEL (authority)
R-08 | DEP-README-COLOR | YES | Correct the staged README key to "teal=Incentivized and amber=Non-incentivized" and re-verify against Display_Map. | REPO-STEW | 2026-08-27T12:00:00+08:00 | YES — before 2026-08-27T14:00 | YES — before 2026-08-28T18:00 | PREREQ-README | T-DEP-README-COLOR
R-09 | CAP-3B | YES | Amend the caption clause to state the 0.07 upper endpoint. | CA-STUDY | 2026-08-27T10:30:00+08:00 | YES — before 2026-08-27T14:00 | YES — before 2026-08-28T18:00 | PREREQ-PROOF | T-CAP-3B
R-10 | RS-3B | YES | Amend the results statement to the 0.07 upper endpoint. | CA-STUDY | 2026-08-27T10:30:00+08:00 | YES — before 2026-08-27T14:00 | YES — before 2026-08-28T18:00 | PREREQ-PROOF | T-RS-3B
R-11 | SUP-F3 | YES | Update the printed supplementary run label to AR-2026-08-24-R17; no file replacement needed. | CA-STUDY | 2026-08-27T10:30:00+08:00 | YES — before 2026-08-27T14:00 | YES — before 2026-08-28T18:00 | PREREQ-PROOF | T-SUP-F3
R-05 | FIG3-D panel | No | Confirm as clear; close the panel task. | PD-EDITOR | 2026-08-27T10:00:00+08:00 | YES — before 2026-08-27T14:00 | YES — before 2026-08-28T18:00 | — | T-D-PANEL
R-06 | CAP-3A | No | No wording change; confirm against the rebuilt legend. | CA-STUDY | 2026-08-27T10:30:00+08:00 | YES — before 2026-08-27T14:00 | YES — before 2026-08-28T18:00 | — | T-CAP-3A
R-07 | RS-3A | No | No change; confirm. | CA-STUDY | 2026-08-27T10:30:00+08:00 | YES — before 2026-08-27T14:00 | YES — before 2026-08-28T18:00 | — | T-RS-3A
R-13 | CAP-3C | No | No wording change; confirm against the corrected annotation. | CA-STUDY | 2026-08-27T10:30:00+08:00 | YES — before 2026-08-27T14:00 | YES — before 2026-08-28T18:00 | — | T-CAP-3C
R-15 | CAP-3D ¦ RS-3D | No | No change; confirm both endpoints. | CA-STUDY | 2026-08-27T10:30:00+08:00 | YES — before 2026-08-27T14:00 | YES — before 2026-08-28T18:00 | — | T-CAP-3D / T-RS-3D
R-12 | DEP-3B | No | Record as verified; release only with the coupled gate. | REPO-STEW | 2026-08-27T12:00:00+08:00 | YES — before 2026-08-27T14:00 | YES — before 2026-08-28T18:00 | PREREQ-ROWS | T-DEP-3B
R-14 | DEP-3C | No | Record as verified; release only with the coupled gate. | REPO-STEW | 2026-08-27T12:00:00+08:00 | YES — before 2026-08-27T14:00 | YES — before 2026-08-28T18:00 | PREREQ-ROWS | T-DEP-3C
R-16 | DEP-3D | No | Record as verified; release only with the coupled gate. | REPO-STEW | 2026-08-27T12:00:00+08:00 | YES — before 2026-08-27T14:00 | YES — before 2026-08-28T18:00 | PREREQ-ROWS | T-DEP-3D
R-17 | DEP-V3 inventory | No | No file replacement; hold unreleased until the coupled gate clears. | REPO-STEW | 2026-08-27T12:00:00+08:00 | YES — before 2026-08-27T14:00 | YES — before 2026-08-28T18:00 | PREREQ-ROWS | —
R-19 | FIG3-LR3 | No | Leave unlinked; route through a scoped request if any part is wanted. | PQL | 2026-08-27T14:00:00+08:00 | YES — before 2026-08-27T14:00 | YES — before 2026-08-28T18:00 | — | —
R-18 | GATE-0147 | Gate | Hold both components; verify all eight corrections, then set the single coupled terminal state. Escalate to the centre director at 2026-08-27T14:30 if any prerequisite is still open. | PQL | 2026-08-27T14:00:00+08:00 | YES — before 2026-08-27T14:00 | YES — before 2026-08-28T18:00 | PREREQ-GATE | —

## 6_Authority_And_Lineage
Part A — recomputed SHA-256 identity links
Object | Workspace file | Recomputed SHA-256 (lowercase) | Asserted at | Result
PRF-02 proof PDF | 04_Proof/current_production_proof_PRF-02.pdf | 6ed5d5954db9225c97e69adba54f9196c7a162c2df060f5c0c3ae4b71c19b347 | proof_component_inventory.json -> proof.proof_sha256 | MATCH
FIG3-LR2 embedded rendition | 04_Proof/figure3_current_proof_extracted.png | 779d11a0b97371edf7296b7818d83c8c5e93ac78da2a67f3b9b31c44e47106b5 | RR-017 p.1/p.2/p.3 attachment SHA-256; inventory embedded_rendition_sha256 | MATCH
FIG3-EST-R17 export | 03_Analysis/fig3_analysis_export_R17.xlsx | cd122e8b72c520eba3c8efa9f96799f3de579f9353cdb6712b337fe6f0c01113 | Accepted_Set!D5; deposit File_Inventory!F2; Dependencies!H7,H8,H10,H12 | MATCH
AM-2026-0147-v5 manuscript | 02_Manuscript/accepted_manuscript_AM-2026-0147-v5.pdf | 58dd21c4f41658c8685861d5eee0c24fd728a2bfb644b82e71ad7bf2503e9935 | Accepted_Set!D2; Version_History!G3 | MATCH
OBS-R17 observations | 03_Analysis/analysis_observations_R17.csv | 7381f1740a23ca4af11b780e78c003869d0590a990e5b984caa7c613555c018c | Run_Manifest!B10; analysis_environment_R17.json input_observations_sha256 | MATCH
All five asserted file-identity links recompute exactly. Per SOP-4.2 §3 this proves identity and never expands approval scope — which is why FIG3-C remains unapproved (R-04) despite the FIG3-LR2 hash matching everywhere it is asserted.
Part B — controlling versus superseded context
Object / version | Lifecycle state | Role in this review | Rollback or invalidation | Locator
AM-2026-0147-v5 | accepted | CONTROLLING for caption and results wording | none (null) | Accepted_Set!A2:H2; Version_History!A3:G3
AM-2026-0147-v4 | superseded | superseded context only | none (null) | Version_History!A2:F2
FIG3-ACC-v5 | accepted baseline | CONTROLLING for any panel outside RR-017 scope — i.e. FIG3-C and FIG3-D | none (null) | Accepted_Set!A3:H3; Version_History!A4:G4
FIG3-LR2 | approved replacement (FIG3-A, FIG3-B only) | CONTROLLING proof component; proof-linked at PRF-02 page[6].image[0] | n/a | proof_component_inventory.json attachment_history.FIG3-LR2; RR-017 p.1-p.3
FIG3-LR3 | orphan attachment | NOT CONTROLLING — time-eligible at 16:40 but all approval and link fields null (R-19) | n/a | proof_component_inventory.json attachment_history.FIG3-LR3; RR-017 p.4
AR-2026-08-24-R17 | approved | CONTROLLING analysis run and display spec | none (null) | Version_History!A6:F6; Run_Manifest!B2; analysis_environment_R17.json
AR-2026-08-18-R16 | superseded | superseded context only — but still the printed SUP-F3 label (R-11) | none (null) | Version_History!A5:G5; AM p.10
DEP-V3 | staged / unreleased | CONTROLLING deposit version; coupled to PRF-02 | none (null) | deposit_version_history.csv row 3; File_Inventory!A2:I2
DEP-V2 | public predecessor (R16) | superseded context only; not a rollback target | none (null) | deposit_version_history.csv row 2
CHK-0147-R16 | historical completed | superseded context only — its four CLEAR states are on FIG3-ACC-v5 under run R16 and confer nothing on the current proof | none (null) | Checklist_History!A2:J2
No eligible rollback or invalidation event exists anywhere in the record (every rollback_event_id is null), so no superseded object returns to control.

## 7_Coverage_And_Method
Scope item required | Covered by | Count | Confirmation
Every Figure 3 panel | R-01, R-02, R-03/R-04, R-05 | 4 of 4 | FIG3-A, FIG3-B, FIG3-C, FIG3-D all reviewed on all ten SOP-4.2 §2 dimensions.
Every linked caption clause | R-06 (CAP-3A), R-09 (CAP-3B), R-13 (CAP-3C), R-15 (CAP-3D) | 4 of 4 | Matches the four caption endpoints in Dependencies (rows 2, 5, 9, 11).
Every linked results statement | R-07 (RS-3A), R-10 (RS-3B), R-15 (RS-3D) | 3 of 3 | Matches the three results endpoints in Dependencies (rows 3, 6, 11). RS-3C is not defined in the dependency map and none is asserted in the proof.
Every linked supplementary reference | R-11 (SUP-F3) | 1 of 1 | Matches Dependencies row 7; printed label and linked file hash assessed as separate fields.
Every linked deposit entry | R-08 (README), R-12 (DEP-3B), R-14 (DEP-3C), R-16 (DEP-3D), R-17 (File_Inventory + DEP-3A-IMM) | 5 of 5 | Covers all four mapped deposit endpoints in Dependencies (rows 4, 8, 10, 12) plus the staged file-identity record.
Coupled release gate | R-18 | 1 | GATE-0147 evaluated under SOP-4.2 §4 precedence.
Unrequested late attachment | R-19 | 1 | FIG3-LR3 explicitly assessed and excluded rather than silently ignored.
Tracker task reconciliation | Sheet 5 "Tracker task" column | 17 of 17 | Every open Verification_Queue task (rows 2-18) maps to at least one register ref.
Release prerequisites | R-08, R-12/R-14/R-16, R-17, R-18 | 4 of 4 | PREREQ-PROOF, PREREQ-README, PREREQ-ROWS and PREREQ-GATE each addressed.
Method and limits
Visual evidence was read from the embedded rendition at PRF-02 page[6].image[0], confirmed pixel-identical to figure3_current_proof_extracted.png. Panel bounds and axis calibration came from proof_component_inventory.json; the registration overlay records coordinates only and asserts no findings.
Structured evidence came from fig3_analysis_export_R17.xlsx (Panel_Estimates and Display_Map), the deposit manifest, the dependency map, the accepted-submission manifest and the approval log. Every figure comparison carries both a visual and a structured-data locator.
The accepted baseline figure was extracted from accepted_manuscript_AM-2026-0147-v5.pdf p.11 and differenced against the proof rendition to establish exactly which panels the FIG3-LR2 replacement changed: FIG3-A and FIG3-B changed within approved scope, FIG3-C changed outside approved scope, FIG3-D is unchanged (0 differing pixels).
Timestamps were normalized to Asia/Singapore and only events at or before 2026-08-26T17:00:00+08:00 were retained. Time-eligibility was treated as necessary but not sufficient for authority, per SOP-4.2 §1.
Corroborating counts: analysis_observations_R17.csv holds 5,280 rows across 48 sections with 5,112 qc_flag=include and 168 exclude_predeclared, matching QC_Summary!B2:B4. This supports the n=42 annotation question being a display-text matter, not a data-extraction matter.
SCOPE LIMIT: this review is confined to production consistency, authorization and release-gate control. It makes no scientific-merit judgement and no causal claim about any estimate, interval or moderator, and it does not re-analyse or reinterpret the study.