## Release Summary
Figure 3 publication-consistency review
Review cutoff | 2026-08-26T17:00:00+08:00
Coupled disposition | RELEASE_AFTER_CORRECTIONS
Current-state instruction | DO NOT RELEASE CURRENT PRF-02 OR DEP-V3
Gate | GATE-0147 / current state QA_REVIEW_OPEN
Production lock | 2026-08-28T18:00:00+08:00
Scope boundary | Publication consistency and release control only; no scientific-merit, interpretation, or causal conclusion.
Decision basis | Mandatory A legend/colour/order, B upper-endpoint, C annotation/authority, B text/run-label, and deposit README corrections; open row checks and final exact-hash coupled reapproval.
Fallback | If not fully closed by PQL at 2026-08-27T14:00:00+08:00, escalate at 14:30 and keep both components held through lock.
Panel outcome at cutoff
Panel | Visible content result | Authority result | Mapped dependency result | Panel disposition | Owner | Due | Blocking now?
FIG3-A | FAIL: label/colour/order | A scope approved, verification condition failed | CAP/RS text pass; deposit README fails; DEP-3A-IMM passes pending explicit check | CORRECT | PD-EDITOR / REPO-STEW | 10:00 / 12:00 Aug 27 | YES
FIG3-B | FAIL: upper 0.11 vs 0.07 | B scope approved, verification condition failed | CAP/RS/SUP fail; deposit row passes pending check | CORRECT + REBUILD | EMC-STAT / CA / PD / REPO | 09:30–12:00 Aug 27 | YES
FIG3-C | FAIL: n=24 vs n=42 | FAIL: C changed outside RR-017 scope | CAP/row pass pending check | RESTORE BASELINE | PD-EDITOR / CA / REPO | 10:00–12:00 Aug 27 | YES
FIG3-D | PASS: all display fields | PASS: unchanged accepted baseline | CAP/RS/row pass pending check | RETAIN + CLOSE | PD-EDITOR / CA / REPO | 10:00–12:00 Aug 27 | NO (but gate open)
Release condition
RELEASE_AFTER_CORRECTIONS is a conditional coupled disposition, not permission to release the current files. PQL may authorize PRF-02 successor proof and DEP-V3 together only after: all FAIL rows are corrected; all PASS rows requiring closeout are verified; the corrected A/B replacement has a newly computed full SHA-256 that is proof-linked and approved by the corresponding author and PQL for exact scope; C is restored to accepted baseline, D is retained, deposit metadata/rows are synchronized, and every Release_Prerequisites row is closed.

## Reconciliation Register
Record ID | Record class | Panel | Endpoint ID | Status | Visibly displayed / current record | Controlling expected value or label | Variance against documented tolerance | Controlling version and approval state | Disposition | Downstream impact | Required action | Primary owner | Due time (+08:00) | Visual locator | Structured-data locator | Authority / lineage locator | Superseded-context note
T-A-PANEL | proof panel verification | FIG3-A | PANEL | FAIL—CORRECTION | Teal mark 0.04 [−0.02, 0.10] is labelled ‘Non-incentivized’; amber mark −0.01 [−0.07, 0.05] is labelled ‘Incentivized’. Legend order is Non-incentivized then Incentivized. Unit and interval label conform. | Teal #148C8C = Incentivized, first; amber #D98B1E = Non-incentivized, second. Geometry: 0.04 [−0.02, 0.10] and −0.01 [−0.07, 0.05]; unit ‘Standardized Δz’; label ‘95% interval’. | Numeric marks: 0.00 axis units / 0 px. Label, colour assignment and order: exact-match failures; categorical fields have no numeric tolerance. | AR-2026-08-24-R17 / FIG3-EST-R17 approved publication export; FIG3-LR2 approved for A under RR-017, conditional on proof-to-R17 verification. | Correct; current proof not releasable. | CAP-3A states the correct mapping but is contradicted by the panel; RS-3A inherits that contradiction; DEP-README-COLOR repeats the wrong proof mapping. | Relabel/reorder the legend without changing the conforming geometry, unit or interval label; include A in the corrected exact-hash A/B replacement and route for author/PQL approval. | PD-EDITOR | 2026-08-27T10:00:00+08:00 | Workspace/04_Proof/current_production_proof_PRF-02.pdf p.6, Figure 3A; Workspace/04_Proof/figure3_current_proof_extracted.png registered bounds x=80–1190, y=90–870; teal interval x=473–785, amber x=345–657. | Workspace/03_Analysis/fig3_analysis_export_R17.xlsx Panel_Estimates!B2:M3; Display_Map!A2:H3 and A8:H9. | Workspace/01_Governance/late_replacement_approval_log.pdf pp.1–3, RR-017 / APPR-RR017-CA / APPR-RR017-PQL; Workspace/04_Proof/proof_component_inventory.json records figure_components.FIG3 and attachment_history.FIG3-LR2. | Workspace/02_Manuscript/accepted_manuscript_AM-2026-0147-v5.pdf p.11 Figure 3A is the accepted baseline; R17 supersedes R16 only for the approved A/B replacement context.
T-B-PANEL | proof panel verification | FIG3-B | PANEL | FAIL—CORRECTION | Median 0.02; lower endpoint −0.01; upper endpoint 0.11. Unit ‘Standardized Δz’ and ‘95% interval’ conform. | Median 0.02; 95% interval [−0.01, 0.07]; same unit/label; native one-pixel and ≤0.005-axis-unit geometry tolerance. | Median 0.00; lower 0.00; upper +0.04 axis units and +104 px (rendered x=1971; expected x=1867). Upper endpoint exceeds both ≤0.005 and ≤1 px limits. | AR-2026-08-24-R17 / FIG3-EST-R17 approved publication export; FIG3-LR2 approved for B under RR-017, conditional on proof-to-R17 verification. | Correct and regenerate; current proof not releasable. | CAP-3B and RS-3B repeat 0.11; SUP-F3 prints the superseded run label; deposit row DEP-3B already carries the R17 value but awaits verification. | Regenerate B from confirmed R17 as 0.02 [−0.01, 0.07]; preserve unit/labels; include B in the corrected exact-hash A/B replacement and route for author/PQL approval. | PD-EDITOR | 2026-08-27T12:00:00+08:00 | Workspace/04_Proof/current_production_proof_PRF-02.pdf p.6, Figure 3B; Workspace/04_Proof/figure3_current_proof_extracted.png bounds x=1210–2320, y=90–870; rendered interval x=1659–1971; registered axis −0.10:0.20. | Workspace/03_Analysis/fig3_analysis_export_R17.xlsx Panel_Estimates!B4:M4; Display_Map!A4:H4 and A8:H9; Workspace/04_Proof/proof_component_inventory.json render_calibration. | Workspace/01_Governance/late_replacement_approval_log.pdf pp.1–3, RR-017 and approval events; Workspace/04_Proof/proof_component_inventory.json attachment_history.FIG3-LR2. | Workspace/02_Manuscript/accepted_manuscript_AM-2026-0147-v5.pdf p.11 Figure 3B / CAP-3B endpoint 0.05 and R16 context are superseded by approved R17 endpoint 0.07.
T-C-PANEL | proof panel verification | FIG3-C | PANEL | FAIL—CORRECTION + AUTHORITY | Median 0.06; 95% interval [0.01, 0.14]; annotation n=24. Unit and interval label conform. | Median 0.06; 95% interval [0.01, 0.14]; exact annotation n=42; accepted baseline authority for C. | Numeric geometry: 0.00 axis units / 0 px. Annotation: n=24 versus n=42, exact-match failure. Authorization: current changed C was not requested or approved. | FIG3-ACC-v5 accepted baseline controls C; approved R17 independently confirms n=42 and the same numeric row. RR-017 expressly says C not requested / not approved. | Restore accepted baseline; current proof not releasable. | CAP-3C correctly says n=42 but is contradicted by the proof image; DEP-3C is numerically correct but its verification remains open. | Restore annotation n=42 exactly and verify no other C pixels changed. Treat C as retained accepted-baseline content, not as an expanded late-replacement scope. | PD-EDITOR | 2026-08-27T10:00:00+08:00 | Workspace/04_Proof/current_production_proof_PRF-02.pdf p.6, Figure 3C; Workspace/04_Proof/figure3_current_proof_extracted.png bounds x=80–1190, y=930–1710; annotation n=24; interval x=550–888. Compare Workspace/02_Manuscript/accepted_manuscript_AM-2026-0147-v5.pdf p.11, Figure 3C (n=42). | Workspace/03_Analysis/fig3_analysis_export_R17.xlsx Panel_Estimates!B5:M5; Display_Map!A5:H5 and A8:H9. | Workspace/01_Governance/accepted_submission_manifest.xlsx Accepted_Set!A3:H3 and Version_History!A4:G4; Workspace/01_Governance/late_replacement_approval_log.pdf pp.1–3 scope matrix excludes C. | The whole late-replacement file hash is approved only for named A/B scope; eligibility or hash linkage does not expand approval to C.
T-D-PANEL | proof panel verification | FIG3-D | PANEL | PASS—RETAIN/CLOSE | Median 0.02; 95% interval [−0.04, 0.08]; category order Incentivized then Non-incentivized; no exploratory marker; unit/interval label conform. | Same geometry, order, absent marker, unit and interval label under accepted-baseline authority; R17 values agree. | All controlled numeric fields 0.00 axis units / 0 px; registered-bounds pixel comparison to accepted baseline found 0 differing pixels; categorical exact matches. | FIG3-ACC-v5 remains controlling for D because RR-017 excluded D; R17 confirms the same display values. | Retain; close verification; no content change. | CAP-3D, RS-3D and DEP-3D conform; only formal mapped checks and coupled re-review remain. | Document the zero-difference registered comparison, retain D unchanged, and close T-D-PANEL. | PD-EDITOR | 2026-08-27T10:00:00+08:00 | Workspace/04_Proof/current_production_proof_PRF-02.pdf p.6, Figure 3D; Workspace/04_Proof/figure3_current_proof_extracted.png bounds x=1210–2320, y=930–1710; interval x=1582–1894. Compare Workspace/02_Manuscript/accepted_manuscript_AM-2026-0147-v5.pdf p.11, Figure 3D. | Workspace/03_Analysis/fig3_analysis_export_R17.xlsx Panel_Estimates!B6:M6; Display_Map!A6:H9. | Workspace/01_Governance/accepted_submission_manifest.xlsx Accepted_Set!A3:H3; Workspace/01_Governance/late_replacement_approval_log.pdf pp.2–3 scope matrix excludes D. | Pixel equality is a registered visual comparison, not an assertion that the full accepted and replacement files are identical.
T-B-EXPORT | analysis confirmation | FIG3-B | FIG3-EST-R17 | PASS—CLOSEOUT REQUIRED | Approved export records 0.02 [−0.01, 0.07]; workbook SHA-256 is cd122e…01113 and matches the staged file-inventory link. | Same R17 estimate, run AR-2026-08-24-R17, approved publication_export state, and exact full-file hash. | 0.00 for all values; hash exact. Administrative confirmation task remains open. | R17 approved 2026-08-25 16:00; attested by EMC-STAT 2026-08-26 08:05; no release status asserted by the attestation. | Confirm and close; do not rerun. | Required before B regeneration and PQL review; no scientific interpretation is requested. | Confirm the R17 values/run/hash on the correction ticket and close T-B-EXPORT. | EMC-STAT | 2026-08-27T09:30:00+08:00 | Not a visual endpoint; linked visual comparison is T-B-PANEL at proof p.6 Figure 3B. | Workspace/03_Analysis/fig3_analysis_export_R17.xlsx Run_Manifest!A2:B11 and Panel_Estimates!A4:M4; Workspace/03_Analysis/analysis_environment_R17.json records analysis_run_id, approval_flag, hashes and attestation. | Workspace/01_Governance/accepted_submission_manifest.xlsx Accepted_Set!A4:H5 and Version_History!A5:G6; Workspace/06_Deposit/deposit_v3_manifest.xlsx File_Inventory!A2:I2. | AR-2026-08-18-R16 is superseded; no rollback event exists.
T-CAP-3A | caption clause | FIG3-A | CAP-3A | PASS TEXT—PANEL BLOCKS | Proof/accepted caption: teal=Incentivized and amber=Non-incentivized. | Same exact R17 display mapping. | Exact text match; 0 variance. It currently conflicts with the visible A legend. | AM-2026-0147-v5 accepted text retained; R17 Display_Map controls current mapping. | Retain text; approve after A correction. | Caption becomes internally consistent only when panel A is corrected. | Verify the corrected panel against unchanged CAP-3A and record wording approval. | CA-STUDY | 2026-08-27T10:30:00+08:00 | Workspace/04_Proof/current_production_proof_PRF-02.pdf p.6, CAP-3A; Workspace/02_Manuscript/accepted_manuscript_AM-2026-0147-v5.pdf p.11, CAP-3A. | Workspace/05_Dependencies/panel_content_dependency_map.xlsx Dependencies!A2:I2; Workspace/03_Analysis/fig3_analysis_export_R17.xlsx Display_Map!A2:H3. | Workspace/01_Governance/accepted_submission_manifest.xlsx Accepted_Set!A2:H2; Workspace/07_Release_Control/author_correction_tracker.xlsx Verification_Queue!A7:L7.
T-RS-3A | results statement | FIG3-A | RS-3A | PASS TEXT—PANEL BLOCKS | Proof: comparison follows the cohort mapping stated in the caption. | Retain the accepted wording, conditional on the corrected panel matching CAP-3A. | No textual variance; current panel makes the reference internally inconsistent. | AM-2026-0147-v5 accepted text; proof wording unchanged. | Retain text; approve after A correction. | Results-to-caption reference is only consistent after panel correction. | Verify RS-3A against corrected panel/CAP-3A and record wording approval. | CA-STUDY | 2026-08-27T10:30:00+08:00 | Workspace/04_Proof/current_production_proof_PRF-02.pdf p.7, RS-3A; Workspace/02_Manuscript/accepted_manuscript_AM-2026-0147-v5.pdf p.8, RS-3A. | Workspace/05_Dependencies/panel_content_dependency_map.xlsx Dependencies!A3:I3; Workspace/03_Analysis/fig3_analysis_export_R17.xlsx Display_Map!A2:H3. | Workspace/01_Governance/accepted_submission_manifest.xlsx Accepted_Set!A2:H2; Workspace/07_Release_Control/author_correction_tracker.xlsx Verification_Queue!A8:L8.
T-DEP-README-COLOR | deposit README entry | FIG3-A | DEP-README-COLOR | FAIL—CORRECTION | Staged text: teal=Non-incentivized and amber=Incentivized. | teal=Incentivized and amber=Non-incentivized. | Both label–colour assignments are reversed; exact-match failure. | DEP-V3 is staged/unreleased and links the approved R17 export; README synchronization prerequisite is open. | Correct staged metadata; do not release deposit yet. | Public deposit description would conflict with corrected panel and caption; coupled gate blocks proof and deposit together. | Replace the README colour key with the exact expected text; verify saved staged record and close PREREQ-README. | REPO-STEW | 2026-08-27T12:00:00+08:00 | No image; mapped visual source is proof p.6 Figure 3A / extracted-image A bounds. | Workspace/06_Deposit/deposit_v3_manifest.xlsx README_Entries!A2:E2 and Release_Prerequisites!A3:F3; Workspace/05_Dependencies/panel_content_dependency_map.xlsx Dependencies!A4:I4; Workspace/03_Analysis/fig3_analysis_export_R17.xlsx Display_Map!A2:H3. | Workspace/06_Deposit/deposit_v3_manifest.xlsx File_Inventory!A2:I2; Workspace/07_Release_Control/production_lock_schedule.md open prerequisites.
QA-DEP-3A-IMM | deposit panel row | FIG3-A | DEP-3A-IMM | PASS—VERIFY/CLOSE (UNLISTED ROW) | Staged row: Incentivized 0.04 [−0.02, 0.10], standardized delta-z, AR-2026-08-24-R17. | Same R17 Incentivized row and run label. | All stored numeric fields 0.00; labels/run exact. The row is panel-mapped by Panel_Data!B2 but is not named in PREREQ-ROWS or the dependency-map rows. | DEP-V3 is staged/unreleased and exact-hash links the approved R17 export. | Retain values; add explicit verification evidence before gate closure. | Without explicit closeout, the register would not cover every staged deposit entry mapped to discrepant panel A. | Verify DEP-3A-IMM against R17 and include it in repository closeout evidence; document that the linked R17 workbook carries the full A estimate set. | REPO-STEW | 2026-08-27T12:00:00+08:00 | Mapped visual source: Workspace/04_Proof/current_production_proof_PRF-02.pdf p.6, Figure 3A (legend currently incorrect). | Workspace/06_Deposit/deposit_v3_manifest.xlsx Panel_Data!A2:H2 and File_Inventory!A2:I2; Workspace/03_Analysis/fig3_analysis_export_R17.xlsx Panel_Estimates!A2:M2. Compare Workspace/05_Dependencies/panel_content_dependency_map.xlsx Dependencies!A2:I4 and Workspace/06_Deposit/deposit_v3_manifest.xlsx Release_Prerequisites!A4:F4 (A row not enumerated). | Workspace/06_Deposit/deposit_version_history.csv DEP-V3 record; Workspace/01_Governance/publication_release_policy.pdf p.5 requires every mapped deposit item synchronized. | This is an existing staged row with conforming values; the finding is the open verification/mapping gap, not a scientific or numeric defect.
T-CAP-3B | caption clause | FIG3-B | CAP-3B | FAIL—CORRECTION | Proof caption says the overall 95% interval extends to 0.11. | R17 upper endpoint 0.07. | +0.04 > 0.005 numeric tolerance; exact numeric echo fails. | PRF-02 current wording conflicts with approved R17 export. | Correct to 0.07 and approve. | Caption otherwise ratifies the erroneous proof whisker. | Change 0.11 to 0.07; verify against corrected B panel and obtain CA wording approval. | CA-STUDY | 2026-08-27T10:30:00+08:00 | Workspace/04_Proof/current_production_proof_PRF-02.pdf p.6, CAP-3B. | Workspace/05_Dependencies/panel_content_dependency_map.xlsx Dependencies!A5:I5; Workspace/03_Analysis/fig3_analysis_export_R17.xlsx Panel_Estimates!D4:F4. | Workspace/07_Release_Control/author_correction_tracker.xlsx Verification_Queue!A10:L10; Workspace/01_Governance/publication_release_policy.pdf p.3 numeric tolerance. | Workspace/02_Manuscript/accepted_manuscript_AM-2026-0147-v5.pdf p.11 endpoint 0.05 is superseded context and is not the correction target.
T-RS-3B | results statement | FIG3-B | RS-3B | FAIL—CORRECTION | Proof results say the overall interval extends to 0.11. | R17 upper endpoint 0.07. | +0.04 > 0.005; exact numeric echo fails. | PRF-02 current wording conflicts with approved R17 export. | Correct to 0.07 and approve. | Results text and caption jointly propagate the erroneous endpoint. | Change 0.11 to 0.07; cross-check CAP-3B and corrected panel; obtain CA wording approval. | CA-STUDY | 2026-08-27T10:30:00+08:00 | Workspace/04_Proof/current_production_proof_PRF-02.pdf p.7, RS-3B. | Workspace/05_Dependencies/panel_content_dependency_map.xlsx Dependencies!A6:I6; Workspace/03_Analysis/fig3_analysis_export_R17.xlsx Panel_Estimates!D4:F4. | Workspace/07_Release_Control/author_correction_tracker.xlsx Verification_Queue!A11:L11; Workspace/01_Governance/publication_release_policy.pdf p.3. | Workspace/02_Manuscript/accepted_manuscript_AM-2026-0147-v5.pdf p.8 endpoint 0.05 is superseded by R17 and must not be restored.
T-SUP-F3 | supplement reference | FIG3-B | SUP-F3 | FAIL—CORRECTION | Accepted supporting-information text prints AR-2026-08-18-R16; stable endpoint SUP-F3 remains linked in the proof. The dependency hash points to the R17 workbook. | Printed run label AR-2026-08-24-R17 while retaining SUP-F3 and linked hash cd122e…01113. | Run-label exact mismatch (R16 vs R17); linked-file hash itself matches R17. | Approved R17 supersedes R16; the printed label and file hash are separate controlled fields. | Update run label; retain stable SUP-F3 ID/hash. | Readers could be directed to a superseded run label even though the linked file is R17. | Update the printed run label to AR-2026-08-24-R17; confirm SUP-F3 ID and R17 hash remain unchanged; approve wording. | CA-STUDY | 2026-08-27T10:30:00+08:00 | Workspace/02_Manuscript/accepted_manuscript_AM-2026-0147-v5.pdf p.10, SUP-F3; Workspace/04_Proof/current_production_proof_PRF-02.pdf p.10, Supporting information. | Workspace/05_Dependencies/panel_content_dependency_map.xlsx Dependencies!A7:I7; Workspace/03_Analysis/fig3_analysis_export_R17.xlsx Run_Manifest!A2:B7. | Workspace/01_Governance/accepted_submission_manifest.xlsx Version_History!A5:G6; Workspace/07_Release_Control/author_correction_tracker.xlsx Verification_Queue!A12:L12. | R16 remains historical context only; no rollback is recorded.
T-DEP-3B | deposit panel row | FIG3-B | DEP-3B | PASS—VERIFY/CLOSE | Staged row: 0.02 [−0.01, 0.07], standardized delta-z, AR-2026-08-24-R17. | Same R17 row and run label. | All numeric fields 0.00; label/run exact. Verification prerequisite remains open. | DEP-V3 staged/unreleased; file inventory exact-hash links the approved R17 export. | Retain row; verify and close. | Correct deposit row must not release ahead of the corrected proof. | Verify DEP-3B and File_Inventory hash/run; close PREREQ-ROWS for B. | REPO-STEW | 2026-08-27T12:00:00+08:00 | Mapped visual source: Workspace/04_Proof/current_production_proof_PRF-02.pdf p.6, Figure 3B (currently incorrect). | Workspace/06_Deposit/deposit_v3_manifest.xlsx Panel_Data!A3:H3, File_Inventory!A2:I2, Release_Prerequisites!A4:F4; Workspace/05_Dependencies/panel_content_dependency_map.xlsx Dependencies!A8:I8. | Workspace/06_Deposit/deposit_version_history.csv record DEP-V3; Workspace/07_Release_Control/production_lock_schedule.md coupled gate.
T-CAP-3C | caption clause | FIG3-C | CAP-3C | PASS TEXT—PANEL BLOCKS | Proof and accepted caption state n=42. | Exact annotation n=42. | Exact text match; current image differs (n=24). | Accepted baseline controls C; R17 confirms n=42. | Retain text; approve restored panel. | Caption is correct but currently contradicted by the unauthorized C image change. | Verify restored n=42 panel against CAP-3C and record wording approval. | CA-STUDY | 2026-08-27T10:30:00+08:00 | Workspace/04_Proof/current_production_proof_PRF-02.pdf p.6, CAP-3C; Workspace/02_Manuscript/accepted_manuscript_AM-2026-0147-v5.pdf p.11, CAP-3C. | Workspace/05_Dependencies/panel_content_dependency_map.xlsx Dependencies!A9:I9; Workspace/03_Analysis/fig3_analysis_export_R17.xlsx Panel_Estimates!L5 and Display_Map!A5:H5. | Workspace/07_Release_Control/author_correction_tracker.xlsx Verification_Queue!A14:L14; Workspace/01_Governance/late_replacement_approval_log.pdf pp.2–3 excludes C.
T-DEP-3C | deposit panel row | FIG3-C | DEP-3C | PASS—VERIFY/CLOSE | Staged row: 0.06 [0.01, 0.14], standardized delta-z, AR-2026-08-24-R17. | Same R17 row. Sample annotation is not stored in this numeric row. | All stored fields 0.00/exact; verification prerequisite remains open. | DEP-V3 staged/unreleased and hash-linked to R17. | Retain row; verify and close. | Correct deposit row remains coupled to the proof’s C annotation correction. | Verify DEP-3C and document that annotation control resides in panel/caption; close PREREQ-ROWS for C. | REPO-STEW | 2026-08-27T12:00:00+08:00 | Mapped visual source: Workspace/04_Proof/current_production_proof_PRF-02.pdf p.6, Figure 3C (annotation currently incorrect). | Workspace/06_Deposit/deposit_v3_manifest.xlsx Panel_Data!A4:H4 and Release_Prerequisites!A4:F4; Workspace/05_Dependencies/panel_content_dependency_map.xlsx Dependencies!A10:I10; Workspace/03_Analysis/fig3_analysis_export_R17.xlsx Panel_Estimates!B5:M5. | Workspace/06_Deposit/deposit_version_history.csv record DEP-V3; Workspace/07_Release_Control/production_lock_schedule.md coupled gate.
T-CAP-3D | caption clause | FIG3-D | CAP-3D | PASS—VERIFY/CLOSE | Caption: Incentivized precedes Non-incentivized; no exploratory marker. | Same exact order and absence. | Exact match. | Accepted baseline controls D; R17 display map agrees. | Retain and close. | No downstream correction; formal mapped check remains. | Verify against retained D panel and record wording approval. | CA-STUDY | 2026-08-27T10:30:00+08:00 | Workspace/04_Proof/current_production_proof_PRF-02.pdf p.6, CAP-3D; Workspace/02_Manuscript/accepted_manuscript_AM-2026-0147-v5.pdf p.11, CAP-3D. | Workspace/05_Dependencies/panel_content_dependency_map.xlsx Dependencies!A11:I11; Workspace/03_Analysis/fig3_analysis_export_R17.xlsx Display_Map!A6:H7. | Workspace/07_Release_Control/author_correction_tracker.xlsx Verification_Queue!A16:L16; Workspace/01_Governance/late_replacement_approval_log.pdf pp.2–3 excludes D.
T-RS-3D | results statement | FIG3-D | RS-3D | PASS—VERIFY/CLOSE | Proof states pre-registered category order and standardized delta-z unit. | Same retained accepted wording and display. | Exact match. | Accepted baseline controls D; proof wording retained. | Retain and close. | No downstream correction; formal mapped check remains. | Verify RS-3D against retained panel/CAP-3D and record wording approval. | CA-STUDY | 2026-08-27T10:30:00+08:00 | Workspace/04_Proof/current_production_proof_PRF-02.pdf p.7, RS-3D; Workspace/02_Manuscript/accepted_manuscript_AM-2026-0147-v5.pdf p.8, RS-3D. | Workspace/05_Dependencies/panel_content_dependency_map.xlsx Dependencies!A11:I11; Workspace/03_Analysis/fig3_analysis_export_R17.xlsx Display_Map!A6:H9. | Workspace/07_Release_Control/author_correction_tracker.xlsx Verification_Queue!A17:L17.
T-DEP-3D | deposit panel row | FIG3-D | DEP-3D | PASS—VERIFY/CLOSE | Staged row: 0.02 [−0.04, 0.08], standardized delta-z, AR-2026-08-24-R17. | Same R17 row. | All fields 0.00/exact; verification prerequisite remains open. | DEP-V3 staged/unreleased and hash-linked to R17. | Retain row; verify and close. | No content correction; coupled release still waits for all prerequisites. | Verify DEP-3D and close PREREQ-ROWS for D. | REPO-STEW | 2026-08-27T12:00:00+08:00 | Mapped visual source: Workspace/04_Proof/current_production_proof_PRF-02.pdf p.6, Figure 3D. | Workspace/06_Deposit/deposit_v3_manifest.xlsx Panel_Data!A5:H5 and Release_Prerequisites!A4:F4; Workspace/05_Dependencies/panel_content_dependency_map.xlsx Dependencies!A12:I12; Workspace/03_Analysis/fig3_analysis_export_R17.xlsx Panel_Estimates!B6:M6. | Workspace/06_Deposit/deposit_version_history.csv record DEP-V3; Workspace/07_Release_Control/production_lock_schedule.md coupled gate.

## Action Plan
Action ID | Required closeout | Primary owner | Due time (+08:00) | Gate purpose | Completion evidence / sign-off
A1 | Complete corrected-proof visual registration for A–D; record pixel/axis checks and C/D baseline comparison. | EMC-QA | 2026-08-27T09:00:00+08:00 | Before production work is accepted | OPEN
A2 | Confirm FIG3-EST-R17 = 0.02 [−0.01, 0.07] for B, run AR-2026-08-24-R17, and SHA-256 cd122e…01113; close T-B-EXPORT without rerun. | EMC-STAT | 2026-08-27T09:30:00+08:00 | Close analysis confirmation | OPEN
A3 | Correct A legend mapping/order and restore C annotation n=42; keep conforming geometry, unit and labels unchanged. | PD-EDITOR | 2026-08-27T10:00:00+08:00 | Mandatory proof corrections | OPEN
A4 | Approve manuscript wording: retain CAP/RS for A/C/D; change CAP-3B and RS-3B to 0.07; change SUP-F3 printed run label to AR-2026-08-24-R17. | CA-STUDY | 2026-08-27T10:30:00+08:00 | Wording approval | OPEN
A5 | Regenerate B as 0.02 [−0.01, 0.07], rebuild the proof/figure, compute the full new hash, and link the corrected A/B replacement; certify C restored and D unchanged. | PD-EDITOR | 2026-08-27T12:00:00+08:00 | Mandatory proof rebuild | OPEN
A6 | Correct DEP-README-COLOR to the R17 mapping; verify DEP-3A-IMM and DEP-3B/3C/3D, File_Inventory run/hash, and keep DEP-V3 staged. | REPO-STEW | 2026-08-27T12:00:00+08:00 | Close repository prerequisites | OPEN
A7 | Approve the exact corrected proof-linked A/B hash after confirming scope; confirm C is restored baseline and D retained; close author approval on the version to publish. | CA-STUDY | 2026-08-27T13:30:00+08:00 | Review-derived deadline before PQL | OPEN
A8 | Perform coupled re-review; require all findings/actions closed and matching proof/deposit state; record RELEASE_AFTER_CORRECTIONS and authorize both together only after closure. | PQL | 2026-08-27T14:00:00+08:00 | Final coupled gate | OPEN
A9 | If any prerequisite remains unresolved, escalate and keep both components held; do not allow production lock to imply release. | PQL → Centre director | 2026-08-27T14:30:00+08:00 | Escalation; absolute lock 2026-08-28T18:00:00+08:00 | OPEN

## Version & Authority Lineage
Lineage ID | Object class | Business / object ID | State at cutoff | Effective time | Hash / UUID (abbrev.) | Precise workspace locator | Control interpretation
L1 | Accepted manuscript | AM-2026-0147-v5 | accepted | 2026-08-19T15:10:00+08:00 | 58dd21c4…e9935 | Workspace/01_Governance/accepted_submission_manifest.xlsx Accepted_Set!A2:H2; Workspace/02_Manuscript/accepted_manuscript_AM-2026-0147-v5.pdf p.1 | Current accepted text baseline.
L2 | Accepted Figure 3 | FIG3-ACC-v5 | accepted baseline | 2026-08-19T15:10:00+08:00 | d64c39d1…3aec5 | Workspace/01_Governance/accepted_submission_manifest.xlsx Accepted_Set!A3:H3 and Version_History!A4:G4; Workspace/02_Manuscript/accepted_manuscript_AM-2026-0147-v5.pdf p.11 Figure 3 | Controls C/D unless valid component-scoped replacement.
L3 | Historical analysis | AR-2026-08-18-R16 | superseded | 2026-08-19T14:00:00+08:00 | — | Workspace/01_Governance/accepted_submission_manifest.xlsx Version_History!A5:G5; Checklist_History!A2:J2 | Historical only; no rollback event.
L4 | Approved analysis/run | AR-2026-08-24-R17 / FIG3-EST-R17 | approved publication export | 2026-08-25T16:00:00+08:00 | cd122e8b…01113 | Workspace/03_Analysis/fig3_analysis_export_R17.xlsx Run_Manifest!A2:B11; Workspace/01_Governance/accepted_submission_manifest.xlsx Accepted_Set!A4:H5; Workspace/03_Analysis/analysis_environment_R17.json | Controls current expected estimates/display; full workbook hash independently recomputed and matched.
L5 | Late replacement request | RR-017 / FIG3-LR2 | CA + PQL approved for A/B only; verification condition | 2026-08-26T12:20:00+08:00 | 779d11a0…106b5 | Workspace/01_Governance/late_replacement_approval_log.pdf pp.1–3; Workspace/04_Proof/proof_component_inventory.json attachment_history.FIG3-LR2 | Exact linked hash and named component scope; C/D expressly excluded.
L6 | Current proof | PRF-02 / page[6].image[0] | author review; QA open | 2026-08-26T09:18:00+08:00 | proof 6ed5d595…b347; image 779d11a0…106b5 | Workspace/04_Proof/proof_component_inventory.json proof and figure_components.FIG3; Workspace/04_Proof/current_production_proof_PRF-02.pdf pp.1,6,14 | Hash link to FIG3-LR2 confirmed; conditional proof-to-R17 check fails A/B and C differs outside scope.
L7 | Later orphan attachment | FIG3-LR3 / Figure3_final_v9.png | orphan; unapproved; not proof-linked | 2026-08-26T16:40:00+08:00 | 536e3d5c…89566 | Workspace/01_Governance/late_replacement_approval_log.pdf p.4; Workspace/04_Proof/proof_component_inventory.json attachment_history.FIG3-LR3 | Eligible by cutoff but has no authority; retained only as history.
L8 | Public predecessor deposit | DEP-V2 | public predecessor / superseded context | 2026-08-19T16:00:00+08:00 | file UUID 96ea08b1… | Workspace/06_Deposit/deposit_version_history.csv DEP-V2 record | R16 predecessor remains public history; no rollback.
L9 | Linked staged deposit | DEP-V3 / HVD-EDU-0147 | staged, unreleased; prerequisites open | 2026-08-26T08:40:00+08:00 | file UUID 0a7d5b4a…; export cd122e8b…01113 | Workspace/06_Deposit/deposit_v3_manifest.xlsx File_Inventory!A2:I2 and Release_Prerequisites!A2:F5; Workspace/06_Deposit/deposit_version_history.csv DEP-V3 record | Authorized R17 file link is exact; README mapping is unsynchronized and row/gate checks remain open.
L10 | Coupled gate | GATE-0147 | QA_REVIEW_OPEN | 2026-08-26T17:00:00+08:00 | — | Workspace/07_Release_Control/production_lock_schedule.md; Workspace/01_Governance/publication_release_policy.pdf pp.5–6 | Recommendation RELEASE_AFTER_CORRECTIONS; current objects remain blocked pending all actions and PQL review.

## Effective Rules
Rule ID | Rule area | Applied rule | Locator
R1 | Evidence cutoff | Retain parseable events at or before cutoff; eligibility does not create authority. | Workspace/01_Governance/publication_release_policy.pdf pp.1–2
R2 | Component authority | Replacement must have exact hash proof-link plus request, CA approval and PQL approval naming the component. | Workspace/01_Governance/publication_release_policy.pdf p.2
R3 | Display equality | Identity, cohort label, colour, category order, median, both endpoints, unit, annotation and authorization must all agree. | Workspace/01_Governance/publication_release_policy.pdf p.3
R4 | Numeric tolerance | Two-decimal absolute difference from round-half-up(source,2) ≤0.005; geometry ≤1 rendered pixel and ≤0.005 axis units. | Workspace/01_Governance/publication_release_policy.pdf p.3
R5 | No curing by median | Matching median does not cure a failed endpoint, label, colour, order, annotation, unit or authority link. | Workspace/01_Governance/publication_release_policy.pdf p.3
R6 | Hash/versions | Recompute full lowercase SHA-256 for file-identity links; hash does not expand scope; successors make prior versions historical absent rollback. | Workspace/01_Governance/publication_release_policy.pdf p.4
R7 | Coupled gate | HOLD > RELEASE_AFTER_CORRECTIONS > RELEASE; unresolved correction, unapproved change, unsynchronized deposit or missing final reapproval blocks both. | Workspace/01_Governance/publication_release_policy.pdf p.5
R8 | Owners/lock | Named role service levels precede PQL re-review and 2026-08-28 18:00 lock. | Workspace/01_Governance/publication_release_policy.pdf p.6; Workspace/07_Release_Control/production_lock_schedule.md